## Slide 1: Strategy
Team Argonauts - EnerNOC
Team: Matt, Dandan, Rui, Sid and Tharanga
Mentors: Bradley, Grace and Mel

## Slide 2: Agenda
Client Goals
High-Level Strategy
Planning
Reporting & Tracking

## Slide 3: Client - EnerNOC
Energy
Suppliers
Demand Response Event
Peak energy usage
Emergency load reduction
Notifications
Execute Energy Reduction Plans
Reduce energy use
Meet reduction goals
Demand Response
Network
Grocery Stores
Factories
Office buildings
Universities

## Slide 4: Business Goals
Ensure that a pragmatic and forward-looking architecture is adopted as part of the Open Automated Demand Response (OpenADR) standard
  Architecture is central to the entire project
    Systemic properties
    Trade spaces
    Traceability to an existing standard
  Implementation provides credence to architecture
    Seeing is believing
    Designs will be copied or adopted in part

## Slide 5: Strategic, Project Plan
SEP’11
OCT’11
NOV’11
DEC’11
JAN’12
FEB’12
MAR’12
Kickoff
Sep 23
Identify
Project,
Business
Goals
EOSP
Define
Refine
SOW/Scope
SRS
WBS
Arch. Drivers
Phase 1 - Inception
Iteration 1
Iterations
2-n
Arch. Refinement
MOSP
Notional
Arch.
Phase 2 - Elaboration

## Slide 6: Strategic, Project Plan
APR’12
MAY’12
JUN’12
JUL’12
AUG’12
…
DEC’12
Iterations
2-n
Arch. Refinement
Stable
Arch.
EOSP
Detailed Design,
Construction, Integration, Testing
EOSP
Transition
Postmortem
Iterations
…
EOSP
Phase 3 - Construction
Phase 2
Phase 4 - Transition

## Slide 7: Planning
Identify project goals
Create initial Project WBS and Project Plan
Develop current Phase plan (# iterations, activities)
Each iteration:
  Iteration planning (pull tasks from Project Plan)
  Execution and tracking
  Revisit Phase and Project Plan

## Slide 8: Planning
Task | Status | Owner
2.1 Task (1hr) | … | …
Adjustments
Tracking
Actual time spent
Tasks completed
Iteration Planning
Estimation
Assignment
WBS
Activities
Deliverables
Master Design Plan
Milestones
Strategy

## Slide 9: Reporting & Tracking
Weekly Status Meetings
  Team status (people)
  Around the table (done, current, issues)
  Project Status
    Project (Where are we?)
    Iteration (Active and upcoming tasks - owners?)
    Phase (Do we need to adjust our plan?)
  Process Reflection
    How are we working and is it helpful?
    Are we tracking our processes appropriately?

## Slide 10: Example Process Reflection
Approach/Tool | Status | Useful? | Purpose/Outcome
Time Tracker | ACTIVE |  | Resources expended
Risk-Register | ACTIVE |  | Continuous risk management
Task List | WIP |  | The current work plan
How do we manage, track, and evaluate our progress?
ARGONAUTS

## Slide 11: Questions and Feedback
Analysis paralysis … Planning has become a full-time activity recently – why?
  Not enough granularity in tasks?
  Not enough budget for ramp-up on tasks?
  Are we just focusing on details we just don’t know right now?
Our goal is to get to a notional architecture ASAP … how ambitious can we be?
  Are we convinced that we will be able to define the architectural drivers by EOS?

## Slide 12: Phase 1 Objectives
Identify architectural drivers traceable to client’s business goals
  Scalability
  Performance
  Fault Tolerance
  Extensibility
  Deployment Costs
Concretely define and prioritized quality attributes
Determine constraints, scope, and preliminary plan

## Slide 13: Phase 2 Objectives
Iteratively develop a stable architecture that reflects the quality attributes outlined in Phase 1
Understand trade-spaces and variability with respect to performance and deployment costs
Systematically reduce uncertainty in the underlying architecture through experimentation

## Slide 14: Phase 3 Objectives
Construct a reference implementation of the architecture designed in Phase 2
Demonstrate systemic properties of the architecture according to the customer’s priorities