## Tasks estimation
| Estimatation tasks for Iterations |  |  |  | Three-Point Estimation
Iteration No | Task Number(*) | Description | Outcome | Owner | Worst Case (man hours) | Most Likely (man hours) | Best Case (man hours) | Effort
4 | 1 | Develop first outline | Every slide to include the title, and notional text of what goes there | Matt | 15 | 10 | 5 | 10
4 | 2 | Collect all time data in one place | All time data collected in one place All estimation data collected in one place | Dandan | 7 | 5 | 2 | 4.8333
4 | 3 | Finish Slide layout and themes |  | Matt | 3 | 2 | 1 | 2
4 | 4 | Project Overview | Team, client, project, deliverables | Matt | 3 | 2 | 1 | 2 | Moved to Iteration
4 | 5 | Project Progress | Where are we in the project? What is the big picture? | Sid | 7 | 5 | 3 | 5 | Backlog
4 | 6 | Requirements (Slides + Proposal) | Slides on requirements elicitation Updated the proposals | Matt | 7 | 6 | 4 | 5.8333
4 | 7 | Planning & Tracking (Slides + Proposal) | Slides on planning and tracking Update the proposals | Rui | 9 | 7 | 5 | 7
4 | 8 | Operations (Slides + Proposal) | Slides on process and operation Update the proposals | Tharanga | 7 | 6 | 4 | 5.8333
4 | 9 | Risks (Slides + Proposal) | Slides on risks and mitigation Update the proposal on risk | Tharanga | 6 | 4 | 3 | 4.1667
4 | 10 | Reflection (Slides) | Slides on overall reflection | Sid | 5 | 3 | 2 | 3.1667
4 | 11 | Roadmap & Future Plans | Slides for roadmap and future plans | Rui | 6 | 4 | 3 | 4.1667
4 | 12 | Prepare and Integrate Slides | Pull together slides and edit | Matt,Sid | 6 | 4 | 3 | 4.1667
4 | 13 | Review Slides as a Team | Team reviews all slides and provides input | Matt,Sid | 10 | 7.5 | 5 | 7.5
4 | 14 | Practice as a Team | Team conducts practice dry-run w/ Sid,Matt | Matt,Sid | 10 | 7.5 | 5 | 7.5
4 | 15 | Dry-Run with Jennifer/Peter | Team conducts practice dry-run w/ Jen,Peter | Matt | 10 | 7.5 | 5 | 7.5
4 | 16 | Dry-Run with Mentors | Team conducts dry-run with mentors | Matt | 10 | 7.5 | 5 | 7.5
4 | 17 | Review SOW as a Team |  | Matt | 7 | 5 | 2.5 | 4.9167
4 | 18 | Decision Milestones | SOW | Matt | 2 | 1 | 0.5 | 1.0833
4 | 19 | Revise SOW | Mentors, Client, Team comments | Matt | 4 | 3 | 1.5 | 2.9167
4 | 20 | Client call Friday |  | Matt | 7 | 5 | 2.5 | 4.9167
4 | 21 | Review Operational Descriptions | ACDM Stage 1, ADS | Matt,Sid | 7.5 | 5 | 2.5 | 5
4 | 22 | Capture Business Constraints | ACDM Stage 1, ADS | Tharanga | 4 | 3 | 2 | 3
4 | 23 | Review Business Constraints |  | Tharanga | 2 | 1.5 | 1 | 1.5
4 | 24 | Capture Technical Constraints | ACDM Stage 1, ADS | Rui | 4 | 3 | 2 | 3
4 | 25 | Review Technical Constraints |  | Rui | 2 | 1.5 | 1 | 1.5
4 | 26 | Format Quality Attributes | ACDM Stage 1, ADS | Dandan | 7 | 4 | 3 | 4.3333
4 | 27 | Review Quality Attributes |  | Dandan | 3.5 | 2 | 1.5 | 2.1667
4 | 28 | Consolidate and update ADS | ACDM Stage 1, ADS | Sid | 4 | 3 | 1.5 | 2.9167
4 | 29 | Review ADS | Team reviews and approves ADS | Sid | 15 | 10 | 7.5 | 10.4167
4 | 30 | Create Master Design Plan | Macro Plan | Rui | 5 | 3 | 2 | 3.1667
4 | 31 | Fix Tracking Tool | New Tracking Tool | Rui | 4 | 2 | 1.5 | 2.25
[5 empty] | 199 | 140 | 88.5 | 141.25
Note on B2: Author: 2 * means the task 2 is the baseline of the estimation

## Iteration 4 plan
Iteration plan
Iteration number | 4
1. Key milestones
Milestone
| Iteration start | 12/05/2011
| Iteration stop | 12/16/2011
2. High-level objectives
EOSP
SOW
SRS
3. Tasks
Task No | Description | Status | Resource | Effort | Start Date | End Date | Duration | Burn down Chart
1 | Develop first outline | DONE1 | Matt | 10 | 2011-12-09 | 2011-12-12 |  | Total Estimate | 140
2 | Collect all time data in one place | DONE2 | Dandan | 4.8333 | 2011-12-09 | 2011-12-12 |  | Work Number | 2
3 | Finish Slide layout and themes | DONE1 | Matt | 2 | 2011-12-09 | 2011-12-12 |  | Work load per week | 70
4 | Project Overview | DONE1 | Matt | 2 | 2011-12-09 | 2011-12-12 |  | Work done in week 1 | 45.4167
5 | Project Progress | DONE2 | Sid | 5 | 2011-12-09 | 2011-12-12 |  | Work done in week 2 | 70.8333
6 | Requirements (Slides + Proposal) | DONE2 | Matt | 5.8333 | 2011-12-09 | 2011-12-12 |  |  | Actual Tasks remaining | Ideal Task remaining
7 | Planning & Tracking (Slides + Proposal) | DONE2 | Rui | 7 | 2011-12-09 | 2011-12-12 |  | week 0 | 140 | 140
8 | Operations (Slides + Proposal) | DONE2 | Tharanga | 5.8333 | 2011-12-09 | 2011-12-12 |  | week 1 | 94.5833 | 70
9 | Risks (Slides + Proposal) | DONE2 | Tharanga | 4.1667 | 2011-12-09 | 2011-12-12 |  | week 2 | 23.75 | 0
10 | Reflection (Slides) | DONE2 | Sid | 3.1667 | 2011-12-09 | 2011-12-12
11 | Roadmap & Future Plans | IN PROGRESS | Rui | 4.1667 | 2011-12-09 | 2011-12-12
12 | Prepare and Integrate Slides | DONE2 | Matt,Sid | 4.1667 | 2011-12-12 | 2011-12-13
13 | Review Slides as a Team | DONE2 | Matt,Sid | 7.5 | 2011-12-12 | 2011-12-13
14 | Practice as a Team | IN PROGRESS | Matt,Sid | 7.5 | 2011-12-12 | 2011-12-13
15 | Dry-Run with Jennifer/Peter | DONE2 | Matt | 7.5 | 2011-12-14 | 2016-12-11
16 | Dry-Run with Mentors | DONE2 | Matt | 7.5 | 2011-12-13 | 2011-12-13
17 | Review SOW as a Team | DONE1 | TEAM | 4.9167 | 2011-12-07 | 2011-12-07
18 | Decision Milestones | DONE1 | Matt | 1.0833 | 2011-12-07 | 2011-12-07
19 | Revise SOW | DONE2 | Matt | 2.9167 | 2011-12-09 | 2016-12-11
20 | Client call Friday | DONE1 | Matt | 4.9167 | 2011-12-09 | 2011-12-09
21 | Review Operational Descriptions | DONE1 | Matt,Sid | 5 | 2011-12-07 | 2011-12-07
22 | Capture Business Constraints | DONE1 | Tharanga | 3 | 2011-12-07 | 2011-12-08
23 | Review Business Constraints | DONE1 | Sid | 1.5 | 2011-12-08 | 2011-12-08
24 | Capture Technical Constraints | DONE1 | Rui | 3 | 2011-12-07 | 2011-12-08
25 | Review Technical Constraints | DONE1 | Matt | 1.5 | 2011-12-08 | 2011-12-08
26 | Format Quality Attributes | DONE1 | Dandan | 4.3333 | 2011-12-07 | 2011-12-08
27 | Review Quality Attributes | DONE1 | Tharanga | 2.1667 | 2011-12-08 | 2011-12-08
28 | Consolidate and update ADS | IN PROGRESS | Sid | 2.9167 | 2011-12-08 | 2011-12-08
29 | Review ADS | NOT STARTED | TEAM | 10.4167 | 2011-12-08 | 2011-12-08
30 | Create Master Design Plan | DONE2 | Rui | 3.1667 | 2011-12-08 | 2012-12-11
31 | Fix Tracking Tool | DONE2 | Rui | 2.25 | 2011-12-07 | 2011-12-07
0
0
0
4.unplaned task
0 | Status meeting | RECURRING | ALL
0 | Client Bi-weekly call | RECURRING | ALL
0 | Mentor meeting | RECURRING | ALL
0 | Client communication | RECURRING | ALL
0 | Iteration Planning Meeting | RECURRING | ALL
0 | Bootcamp lecture | RECURRING | ALL
0 | Recording Time | RECURRING | ALL
0 | Preparation for Status Meetings | RECURRING | ALL

## Iteration 4 week 1 time track
Iteration 4 Time tracking week 1
| Total Time | 125.836
|  | 92.856 | 13.03 | 10.65 | 9.3
1. Planed task
Task No | Description | M | T | R | D | S
1 | Develop first outline | 2.4 | 1.7 | 1.8 | 2.1 | 2.25
2 | Collect all time data in one place
3 | Finish Slide layout and themes
4 | Project Overview
5 | Project Progress |  |  |  |  | 5
6 | Requirements (Slides + Proposal) | 8.5 | 2.5
7 | Planning & Tracking (Slides + Proposal) |  |  | 2 |  | 3
8 | Operations (Slides + Proposal) |  | 2.1
9 | Risks (Slides + Proposal) |  | 0.6
10 | Reflection (Slides)
11 | Roadmap & Future Plans
12 | Prepare and Integrate Slides
13 | Review Slides as a Team
14 | Practice as a Team
15 | Dry-Run with Jennifer/Peter
16 | Dry-Run with Mentors
17 | Review SOW as a Team | 1.6 | 1.6 | 1.6 | 1.6
18 | Decision Milestones | 1.5
19 | Revise SOW | 2
20 | Client call Friday | 2.3 | 1.25 | 1.25 | 1.25 | 1.25
21 | Review Operational Descriptions | 2 |  |  | 0.6 | 2.5
22 | Capture Business Constraints |  | 2.33
23 | Review Business Constraints |  |  |  |  | 0.5
24 | Capture Technical Constraints |  |  | 1
25 | Review Technical Constraints | 0.683
26 | Format Quality Attributes |  |  |  | 3.5
27 | Review Quality Attributes |  | 0.45
28 | Consolidate and update ADS | 0.83 |  |  |  | 1.75
29 | Review ADS |  | 0.5 |  | 0.25
30 | Create Master Design Plan |  |  | 2
31 | Fix Tracking Tool |  |  | 1
| Sum of time cost | 71.043
4.unplaned task
0 | Status meeting
0 | Client Bi-weekly call
0 | Mentor meeting
0 | Client communication
0 | Iteration Planning Meeting
0 | Bootcamp lecture
0 | Recording Time
0 | Preparation for Status Meetings

## Iteration 4 week 2 time track
Iteration 4 week 2 Time tracking
1. Planed task
Task No | Description | M | T | R | D | S
1 | Develop first outline
2 | Collect all time data in one place
3 | Finish Slide layout and themes | 5 | 5 | 5 | 5 | 5
4 | Project Overview | 4
5 | Project Progress | 3 | 0.5 |  |  | 0.25
6 | Requirements (Slides + Proposal) | 1
7 | Planning & Tracking (Slides + Proposal) |  |  | 1
8 | Operations (Slides + Proposal) |  | 2.75
9 | Risks (Slides + Proposal) | 2 | 1.75 |  | 2.5
10 | Reflection (Slides) | 3 | 0.66 |  |  | 10
11 | Roadmap & Future Plans | 4
12 | Prepare and Integrate Slides | 13 | 33.75 | 24 | 13 | 15
13 | Review Slides as a Team | 7 |  |  | 7 | 5
14 | Practice as a Team | 8 |  |  | 8 | 5
15 | Dry-Run with Jennifer/Peter | 1.5 |  | 1.2 | 1.2 | 1.2
16 | Dry-Run with Mentors | 1.2 | 1.2 | 1.2 | 1.2 | 1.2
17 | Review SOW as a Team |  | 1.5 |  | 1.5
18 | Decision Milestones
19 | Revise SOW | 0.75
20 | Client call Friday
21 | Review Operational Descriptions
22 | Capture Business Constraints
23 | Review Business Constraints
24 | Capture Technical Constraints
25 | Review Technical Constraints
26 | Format Quality Attributes
27 | Review Quality Attributes
28 | Consolidate and update ADS
29 | Review ADS
30 | Create Master Design Plan
31 | Fix Tracking Tool
| Total time cost in week 2 | 215.01
4.unplaned task
0 | Status meeting
0 | Client Bi-weekly call
0 | Mentor meeting | 0.5 |  |  |  | 0.5
0 | Client communication
0 | Iteration Planning Meeting
0 | Bootcamp lecture
0 | Recording Time
0 | Preparation for Status Meetings

## Project Plan
Project Phase / Iteration / Activities | Start date | Duration | End date | Activity Owner | Inputs | Outputs
Inception / Iteration 1 | 2011-10-16 | 14 | 2011-10-29
Iteration Planning Activity - Review WBS - Define Iteration Objectives - Define Evaluation Criteria - Review Risks - Identify Tasks - Estimation - Assignment |  |  |  |  | WBS Risk Register | WBS (Updated) Risk Register (Updated) Iteration 1 Plan (Created)
Iteration Tracking Activity - Weekly Status Meeting - Weekly Status Email to Client - Bi-weekly Conference Call - Daily Stand-up Meeting |  |  |  |  | Iteration 1 Plan Action Items List Risk Register Client Communication Log | Iteration 1 Plan (Updated) Action Items List (Updated) Risk Register (Updated) Client Communication Log (Updated)
Iteration Assessment Activity - Review Iteration Plan - Review Process - Review Project Plan - Review Project Scope |  |  |  |  | Iteration 1 Plan Project Plan | Iteration 1 Summary (Created) Project Plan (Updated) SOW (Updated and Refined)
Identify Architectural Drivers |  |  |  |  | OpenADR Documents Client Communication Log | SRS Version 0.1 (Created)
OpenADR Familiarization
Develop Macro Strategy and Plan |  |  |  |  | Bootcamp Presentations | Project Plan (Created)
Establish Iteration Structure | [5 empty] | Process Guide (Created)
Inception / Iteration 2 | 2011-10-30 | 14 | 2011-11-12
Iteration Planning Activity |  |  |  |  | Iteration 1 Plan WBS Risk Register | WBS (Updated) Risk Register (Updated) Iteration 2 Plan (Created)
Iteration Tracking Activity |  |  |  |  | Iteration 2 Plan Action Items List Risk Register Client Communication Log | Iteration 2 Plan (Updated) Action Items List (Updated) Risk Register (Updated) Client Communication Log (Updated)
Iteration Assessment Activity |  |  |  |  | Iteration 2 Plan Project Plan | Iteration 2 Summary (Created) Project Plan (Updated)
Refine Quality Attributes |  |  |  |  | SRS Version 0.1 | SRS Version 0.2 (Updated)
Identify High-Level Functional Requirements |  |  |  |  | SRS Version 0.1 | SRS Version 0.2 (Updated)
Update SOW |  |  |  |  | SOW Version 0.1 | SOW Version 0.2 (Updated)
Establish Quality Metrics |  |  |  |  | Plan Proposal 0.1 | Plan Proposal 0.2
Inception / Iteration 3 | 2011-11-13 | 21 | 2011-12-03 |  | Iteration 2
Iteration Planning Activity |  |  |  |  | Iteration 2 Plan WBS Risk Register | WBS (Updated) Risk Register (Updated) Iteration 3 Plan (Created)
Iteration Tracking Activity |  |  |  |  | Iteration 3 Plan Action Items List Risk Register Client Communication Log | Iteration 3 Plan (Updated) Action Items List (Updated) Risk Register (Updated) Client Communication Log (Updated)
Iteration Assessment Activity |  |  |  |  | Iteration 3 Plan Project Plan | Iteration 3 Summary (Created) Project Plan (Updated)
Refine Architectural Drivers |  |  |  |  | SRS Version 1.1 | SRS Version 1.2 (Updated)
Refine Notional Architecture |  |  |  |  | Notional Arch Version 1.0 | Notional Arch Version 1.1 (Updated)
Inception / Iteration 4 | 2011-12-04 | 14 | 2011-12-17
Iteration Planning Activity |  |  |  |  | Iteration 3 Plan WBS Risk Register | WBS (Updated) Risk Register (Updated) Iteration 4 Plan (Created)
Iteration Tracking Activity |  |  |  |  | Iteration 4 Plan Action Items List Risk Register Client Communication Log | Iteration 4 Plan (Updated) Action Items List (Updated) Risk Register (Updated) Client Communication Log (Updated)
Iteration Assessment Activity |  |  |  |  | Iteration 4 Plan Project Plan | Iteration 4 Summary (Created) Project Plan (Updated)
Elaboration / Iteration 1 | 2011-10-16 |  | 2011-10-28
Iteration Planning Activity - Review WBS - Define Iteration Objectives - Define Evaluation Criteria - Review Risks - Identify Tasks - Estimation - Assignment |  |  |  |  | WBS Risk Register | WBS (Updated) Risk Register (Updated) Iteration 1 Plan (Created)
Iteration Tracking Activity - Weekly Status Meeting - Weekly Status Email to Client - Bi-weekly Conference Call - Daily Stand-up Meeting |  |  |  |  | Iteration 1 Plan Action Items List Risk Register Client Communication Log | Iteration 1 Plan (Updated) Action Items List (Updated) Risk Register (Updated) Client Communication Log (Updated)
Iteration Assessment Activity - Review Iteration Plan - Review Process - Review Project Plan |  |  |  |  | Iteration 1 Plan Project Plan | Iteration 1 Summary (Created) Project Plan (Updated)

## Iteration 1 Plan
Iteration 1 plan
1. Key milestones
| Milestone | Date
| Iteration start | 2011-10-16
| Client meeting | 2010-10-28
| Iteration stop | 2010-10-29
2. High-level objectives
Tailor ACDM process
Discussion quality attributes
SRS draft version
3. Work Item assignments
| Name or key words of description | Priority | Size estimate (points) | State | Reference material | Target iteration | Assigned to (name) | Estimate Time cost | Hours worked | Estimate of hours remaining
| Read OpenADR document and identify quality attributes | high |  | Done | OpenADR specification doc(dropbox) |  | Team | 3 FOR EACH | 3 | 0
| Document quality attributes & constrains | high |  | Done |  |  | Tharanga | 9 | 4.5 | 0
| Tailor processes from ACDM | high |  | Done | ACDM white paper |  | SID | 5 | 4
| Plan for iteration 1 | Medium |  | Done |  |  | RUI | 4 | 4 | 0
| High level plan for iteration 2 and 3 | Medium |  | In progress |  |  | RUI ,MATT,SID | 5 FOR Each | 3.3667
Total:
4. Evaluation criteria
Client meeting minutes including the clients comments on quality attributes
A one or two page doc including the process
Iteration plan don google docs
5. Time cost on things not in the assignment
| Name or key words of description | Purpose | State | Your name | Hours worked | Estimate of hours remaining
| Learning openUP for iteration planning | iteration plan template | done | Rui | 1 | 0
| Client Meeting + After Meeting Discussion | Client | Done | Rui | 1.5
| Status Meeting + After Meeting Dsicussion | Mentoring | Done | Rui | 0.75
| Bootcamp Lectures + After class discussion | Lectures/Class | Done | Rui | 3
| Extra Hour Open ADR Reading |  | Done | Rui | 2
| Weekly Status Meeting | Status Mtg | done | Matt | 0.55
| Client Bi-weekly call | Client | done | Matt | 0.91667
| Document Quality Attributes & Constraints | SRS |  | Matt | 3.8167
| Iteration Reflection Meeting | Meeting | done | Matt | 0.26667
| Mentor Meeting | Mentoring | done | Matt | 0.7
| Coordination, Emails, Overhead | Team |  | Matt | 1.45
| Recording Time | Time |  | Matt | 0.33333
| Bootcamp Lectures | Lectures/Class | Done | Sid | 2.5
| Mentor meet | Mentoring | Done | Sid | 0.5
| Meetings (SRS Meeting, Conf call, status meeting, team time, planning meeting) | planning, tracking, co-ordination, synchronization | Done | Sid | 4.25
| Bootcamp Lectures + After class discussion | Lectures/Class | Done | Dandan | 3
| Client Meeting + After Meeting Discussion | Client | Done | Dandan | 1.5
| Status Meeting + After Meeting Dsicussion | Mentoring | Done | Dandan | 0.75
| Mentor Meeting | Mentoring | Done | Dandan | 0.25
| Extra Hour Open ADR Reading | Study | Done | Dandan | 2
| SRS Discussion + Review | Documentation | Done | Dandan | 2
|  |  |  | Total: | 33.0333
6.open questions
Question description

## Iteration 2 Plan
Iteration 2 plan
1. Key milestones
| Milestone |  | Date |  |  |  | Available Hours
| Iteration start |  | 2011-10-30
70 hours
[10 empty] | Total Hours Available | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | Individual Hours Mean | Standard Deviation for Individual Hours | Total Estimated Hours | Total Touched Task Estimated Hours | Total Time Spent on Tasks* | Time Spent / Time Estimated
| Iteration stop |  | 2011-11-12 | [6 empty] | Overhead Estimate | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 25.5 | 4 | 191.7 | 110.8 | 42.02 | 0.3792
[10 empty] | Available (hours) | 14 |  | 14 |  | 14 |  | 14 |  | 14
2. High-level objectives | [9 empty] | Assigned (hours) | 12.8 | 12.8 | 19.2 | 19.2 | 14.4 | 14.4 | 19.2 | 19.2 | 14.4 | 14.4
| Refine Quality Attributes | [8 empty] | Spent on Project (hours) | 6.75 | 8.61 | 3.23 | 3.4 | 1.3 | 4.6 | 6.25 | 4 | 2.75 | 6.5
| Identify High-Level Functional Requirements | [8 empty] | Spent on Overhead (hours) | 7.5767 | 8.28 | 9.64 | 10 | 7.55 | 6.2 | 6.55 | 8.5 | 8.5 | 5.5
| Update SOW | [8 empty] | Total Hours Remaining | -7.2167 |  | -2.27 |  | 4.35 |  | -1.3 |  | 0.75
Identify Quality Metrics
3. Work Item assignments
| Description | Outcome | Priority | Overhead? | Status | Reference material | Size Estimate (Planning Poker) | Assigned (ALL,SDRTM) | Total Estimate (hours) | Total Actuals (hours) | M | M | T | T | R | R | D | D | S | S | Start Date | End Date
0 | Bootcamp lecture |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 24.17 | 2.27 | 2.7 | 2.25 | 2.5 | 2.25 | 2.5 | 2.25 | 2.7 | 2.25 | 2.5
0 | Status meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 11.08 | 0.7 | 1.08 | 2.85 | 2.5 | 0.75 |  | 0.7 | 0.75 | 0.75 | 1
0 | Client Bi-weekly call |  |  |  | RECURRING |  |  | ALL |  | 4.82 | M: 0.92; T: 0.9; R: 1; D: 1; S: 1
0 | Mentor meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 5.5467 | 0.66667 | 0.58 | 0.55 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.75
0 | Client communication |  |  |  | RECURRING |  |  | ALL |  | 3.12 | M: 0.67; M: 1.12; T: 0.33; R: 1
0 | Iteration Planning Meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 17.42 | M: 3.48; T: 3.34; R: 3.75; D: 3.1; S: 3.75
0 | Iteration Reflection Meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 5.3 | M: 0.7; T: 1.2; R: 1.3; D: 1.1; S: 1
0 | Recording Time |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 1.35 | 0.3 | 0.25 | 0.15 | 0.15 |  |  |  | 0.25 | 0.25
0 | Preparation for Status Meetings |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 2.81 | 0.16 | 0.6 | 0.5 |  | 0.3 |  |  |  | 1 | 0.25
1 | (Just-In-Time Learning) Read Architecture in Practice | Chapters 4,5 | HIGH |  | DONE | Chapters 4,5 | 15 | ALL | 24 | 8.45 | M: 1.5; T: 1.65; R: 1.3; D: 2; S: 2 | 2011-11-02 | 2011-11-03
2 | Split and Agree on Format of Capturing QAs | Update SRS s5 | HIGH |  | DONE | Chapter 4 | 5 | ALL | 8 | 2.75 | M: 0.75; T: 1.25; S: 0.75 | 2011-11-03 | 2011-11-03
3 | Performance | One scenario per checklist item | HIGH |  | DONE |  | 5 | S | 8 | 2.75 | S: 2.75 | 2011-11-04 | 2011-11-08
4 | Scalability | One scenario per checklist item | HIGH |  | DONE |  | 8 | D | 12.8 | 4.25 | D: 4.25 | 2011-11-04 | 2011-11-08
5 | Security | One scenario per checklist item | MED |  | CLOSED |  | 5 |  | 8 | 0
6 | Modifiability | One scenario per checklist item | MED |  | CLOSED |  | 5 |  | 8 | 0
7 | Availablility | One scenario per checklist item | MED |  | CLOSED |  | 5 |  | 8 | 0
8 | Testability | One scenario per checklist item | MED |  | CLOSED |  | 8 |  | 12.8 | 0
9 | List High-Level Functionality of OpenADR | Create SRS s4 | LOW |  | MOVED TO iteration 3 |  | 13 |  | 20.8 | 1.7 | M: 1.7
10 | SOW Section 2 | Update SOW | LOW |  | MOVED TO iteration 3 |  | 3 |  | 4.8 | 0
11 | SOW Section 3,4 | Update SOW | LOW |  | MOVED TO iteration 3 |  | 3 |  | 4.8 | 0
12 | Identify appropriate quality metrics & controls | List | MED | OVERHEAD | MOVED TO iteration 3 |  | 5 |  | 8 | 0
13 | Select high-priority metrics & controls | Prioritized List | MED | OVERHEAD | MOVED TO iteration 3 |  | 5 |  | 8 | 0
14 | Incorporate metrics & controls into process | Create Tracking Artifacts | LOW | OVERHEAD | MOVED TO iteration 3 |  | 8 |  | 12.8 | 0
15 | Investigate QAW | Talk to expert, email team | MED |  | MOVED TO iteration 3 |  | 2 |  | 3.2 | 0
16 | Develop project resource chart | Excel chart | HIGH | OVERHEAD | NOT STARTED |  | 3 | T | 4.8 | 0.75 | T: 0.75 | 2011-11-02 | 2011-11-07
17 | Create official project milestone chart | 1-Page View | HIGH |  | DONE |  | 3 | M | 4.8 | 4.33 | M: 2.13; M: 2.2 | 2011-11-02 | 2011-11-07
18 | Update project plan with milestones, hard + soft | Update Project Plan | HIGH |  | DONE |  | 1 | M | 1.6 | 0.58 | M: 0.58 | 2011-11-02 | 2011-11-07
19 | Tailor ACDM | Update Process Guide | HIGH | OVERHEAD | MOVED TO iteration 3 |  | 5 | T | 8 | 3.55 | M: 1.15; T: 2.4 | 2011-11-02 | 2011-11-11
20 | Update WBS in proper format | Formal WBS | HIGH | OVERHEAD | DONE |  | 3 | R | 4.8 | 1.82 | M: 1.22; R: 0.6 | 2011-11-02 | 2011-11-07
21 | Bootcamp planning presentation | Presentation, practice | HIGH | OVERHEAD | DONE |  | 2 | R | 3.2 | 1.3 | R: 1.3 | 2011-11-02 | 2011-11-07
22 | review SRS(indiviudual ) | SRS 0.2 | HIGH |  | DONE |  |  | ALL | 0 | 3.22 | M: 1.87; T: 0.6; S: 0.75 | 2011-11-08 | 2011-11-10
23 | review SRS(team ) | SRS 0.2 | HIGH |  | DONE |  |  | ALL | 0 | 5.82 | M: 1.92; T: 1.9; S: 2 | 2011-11-10 | 2011-11-10
24 | proof SRS(indiviudual ) | SRS 0.2 | HIGH |  | MOVED TO iteration 3 |  |  | M | 0 | 0 | [10 empty] | 2011-11-11 | 2011-11-11
| Incorporate time usage metrics into time tracker | Iteration 2 Plan |  | UNPLANNED | DONE | [5 empty] | M: 0.91667
| Research on Arch | [9 empty] | R: 2.6
4. Evaluation criteria
Note on E16: We track Overhead items separately. Refer to the MSELi definition of overhead Version 1.0
Note on F16: DONE IN PROGRESS NOT STARTED BACKLOG RECURRING

## Iteration 3 plan
h
| Milestone |  | Date
| Iteration start |  | 2011-11-13
[10 empty] | Total Hours Available | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  |  | Individual Hours Mean | Standard Deviation for Individual Hours | Total Estimated Hours | Total Touched Task Estimated Hours | Total Time Spent on Tasks | Time Spent / Time Estimated
| Iteration stop |  | 2011-12-02 | [6 empty] | Overhead Estimate | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  |  |  | 90
[10 empty] | Available (hours) | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14
2. High-level objectives | SOW | [8 empty] | Assigned (hours) | 20 | 20 |  | 25.4667 | 25.4667 |  | 12.6667 | 12.6667 |  | 12.6667 | 12.6667 |  | 24 | 24
| Identify High-Level Functional Requirements | [8 empty] | Spent on Project (hours) | 7.04 | 11.47 |  | 7.83 | 2.66 |  | 1.3 | 0 |  | 9.1 | 0 |  | 7.5 | 2
| Prepare for EOSP | [8 empty] | Spent on Overhead (hours) | 13.62 | 4.316 |  | 12.05 | 4.72 |  | 5.55 | 0 |  | 12.25 | 0 |  | 7.5 | 4
[10 empty] | Total Hours Remaining | -12.446 |  |  | -3.26 |  |  | 17.15 |  |  | 2.65 |  |  | 3
3. Work Item assignments
| Description | Outcome | Priority | Overhead? | Status | Reference material | Size Estimate (Planning Poker) | Assigned (ALL,SDRTM) | Total Estimate (hours) | Total Actuals (hours) | M | M | M | T | T | T | R | R | R | D | D | D | S | S | S | Start Date | End Date
0 | Bootcamp lecture |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 19.13 | 2.23 |  | 1.25 | 2.25 |  | 2.4 | 2.25 |  | 1.5 | 2.25 |  | 1.25 | 2.25 |  | 1.5
0 | Status meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 9.563 | 0.8 | 0.333 | 1.08 | 0.8 |  | 0.75 | 0.8 |  | 1.25 | 0.75 |  | 1 | 0.75 |  | 1.25
0 | Client Bi-weekly call |  |  |  | RECURRING |  |  | ALL |  | 0
0 | Mentor meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 6.08 | 0.58 | 0.67 | 0.58 | 0.5 |  |  | 0.5 |  | 0.5 | 0.75 |  | 0.5 | 0.5 | 0.5 | 0.5
0 | Client communication |  |  |  | RECURRING |  |  | ALL |  | 3.87 | M: 1.21; M: 1.32; M: 1.34
0 | Iteration Planning Meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 9.83 | M: 1.83; T: 2; R: 2; D: 2; S: 2
0 | Iteration Reflection Meeting |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 0
0 | Recording Time |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 1.35 | M: 0.25; M: 0.38; M: 0.2; T: 0.02; D: 0.5
0 | Preparation for Status Meetings |  |  | OVERHEAD | RECURRING |  |  | ALL |  | 3.12 | M: 1; M: 0.62; R: 0.75; S: 0.75
0 | Studio Presentation | [8 empty] | 2.33 | T: 1; T: 1.33
0 | Studio Discussion | [8 empty] | 2.99 | T: 1.33; T: 1.66
2 | Template for functional requirements | Post in Google Docs |  |  | DONE |  | 2 | T | 1.3333 | 2.03 | T: 2.03 | 2011-11-18 | 2011-11-19
3 | Functional requirement capture | Post in Google Docs |  |  | DONE | -Whitepaper -Client communications log -Len's white paper |  |  |  | 11.28 | M: 7.28; D: 2; S: 2
| from white paper |  |  |  | DONE | Open ADR | 5 | R | 3.3333 | 3 | R: 2; S: 1 | 2011-11-19 | 2011-11-21
| from client comm log |  |  |  | DONE | Open ADR | 3 | D | 2 | 2.5 | D: 2; S: 0.5 | 2011-11-19 | 2011-11-21
4 | Review functional requirements and consolidate | Review In Google Docs |  |  | IN PROGRESS |  | 15 | ALL | 10 | 7.25 | M: 2; T: 2.25; S: 3
5 | Update SRS doc (style and formatting) | Updated SRS Word Document with consolidated info |  |  | BACKLOG |  | 2 | S | 1.3333 | 0
6 | Create Logical Architecture, prepare for client discussion, Risk analysis | -Logical architecture -List of risks that the team is likely to face in the future |  |  | DONE |  | 25 | ALL | 16.6667 | 14.08 | M: 2.58; T: 3; D: 4.5; S: 4
7 | Client Skype call | Update client communications log |  |  | DONE |  | 15 | ALL | 10 | 8.92 | M: 2.22; T: 1.8; R: 1.3; D: 1.6; S: 2
8 | Write the SOW | Updated SOW |  |  | DONE |  | 8 | M | 5.3333 | 10.26 | M: 1.03; M: 8.15; M: 0.58; T: 0.5
9 | Update Planning proposal | One tab for each method we are using |  | OVERHEAD | DONE |  | 5 | S | 3.3333 | 3.75 | M: 0.5; M: 1; S: 2.25
10 | Update Defining the Problem Proposal | One tab for each method we are using |  | OVERHEAD | DONE |  | 5 | S | 3.3333 | 1.25 | S: 1.25
11 | Update Operations Proposal | One tab for each method we are using |  | OVERHEAD | DONE |  | 5 | S | 3.3333 | 1.75 | S: 1.75
12 | Create Design Proposal | One tab for each method we are using |  | OVERHEAD | IN PROGRESS |  | 3 | M | 2 | 0
13 | Determine structure of EOSP | Outline and structure of EOSP |  | OVERHEAD | DONE | Other prior EOSP from Dogbert | 25 | ALL | 16.6667 | 4.4 | T: 1.2; D: 1.2; S: 1; S: 1
14 | Determine major lessons learned | Statement of major lessons learned |  | OVERHEAD | DONE |  | 15 | ALL | 10 | 5 | bar: M; T; R; D; S
15 | Close out Iteration 2 Tasks and move backlog to Iteration 3 | Iteration 3 Backlog |  | OVERHEAD | DONE |  | 2 |  | 1.3333 | 0.5 | R: 0; R: 0.5
16 | Configuration Management Plan | 1 document describing what goes where on GDocs, Git, and Dropbox |  | OVERHEAD | BACKLOG |  |  |  |  | 1.283 | M: 0.5; M: 0.783
17 | Identify appropriate quality metrics & controls | List | MED | OVERHEAD | BACKLOG |  | 5 |  | 8 | 0
18 | Select high-priority metrics & controls | Prioritized List | MED | OVERHEAD | BACKLOG |  | 5 |  | 8 | 0
19 | Incorporate metrics & controls into process | Create Tracking Artifacts | LOW | OVERHEAD | BACKLOG |  | 8 |  | 12.8 | 0
20 | Investigate QAW | Talk to expert, email team | MED |  | DONE |  | 2 |  | 3.2 | 0
21 | Develop project resource chart | Excel chart | HIGH | OVERHEAD | BACKLOG |  | 3 | T | 4.8 | 0.75 | T: 0.75 | 2011-11-02 | 2011-11-07
22 | Tailor ACDM | Update Process Guide | HIGH | OVERHEAD | DONE | Tony's white paper Tony's book | 5 | T | 8 | 10.68 | M: 1.15; M: 0.98; T: 0.5; T: 2.25; T: 3.8; D: 1; S: 1 | 2011-11-02 | 2011-11-11
23 | ACDM Overview with Tony | Introduction to ACDM | HIGH | OVERHEAD | UNPLANNED |  |  |  |  | 6.78 | M: 1.68; T: 1.7; T: 1.7; D: 1.7
24 | Poster Session |  |  | OVERHEAD | UNPLANNED |  |  |  |  | 9.85 | M: 3.25; T: 3.3; D: 3.3
25 | Meeting w/ Matt Bass on Architecture |  |  | OVERHEAD | UNPLANNED |  |  |  |  | 3 | bar: M; T; D
26 | Protocol Research |  |  |  | UNPLANNED |  |  |  |  | 4 | M: 2; R: 2
27 | Speak with Tony on Architecture & Risk (2 Dec) |  |  |  | UNPLANNED |  |  |  |  | 1.83 | M: 0.83; T: 1
28 | Initial Risk Analysis for Project |  |  |  | UNPLANNED |  |  |  | 134.8 | 1 | bar: M
[10 empty] | 3 | D: 3
Note on E14: We track Overhead items separately. Refer to the MSELi definition of overhead Version 1.0
Note on F14: type here --siddharth.subu Sun Nov 20 2011 21:11:05 GMT-0500 (Eastern Standard Time) DONE IN PROGRESS NOT STARTED BACKLOG RECURRING BLOCKED