## EV
Legend | Not started | InProgress - Missed deadlines | InProgress - Current | Completed
Iteration | Work package # | Work Package | Expected Completion Week | Actual Completion Week | Estimate (man hours) | Value | ONE WEEK |  | TWO WEEKS | 322
12 | 1 | Tools and Infrastrcture |  |  | 35 | 4
12 | 3 | Security design and Exp. |  |  | 42 | 5
12 | 2 | Protocol Ext. Exp. | Week 1 | Week 1 | 94 | 12 | 21
13 | 1 | AWS training |  |  | 30 | 4
13 | 2 | Database design and implement | Week2 | Week2 | 190 | 24 | 49
14 | 1 | Creating Solution According to the static architecture |  |  | 35 | 4
14 | 2 | Core Connector module - Experiment- Design- Implement |  |  | 56 | 7 |  | 60
14 | 3 | Core Message module - Experiment- Design- Implement |  |  | 26 | 3
14 | 4 | QA Tools | Week3 | Week3 | 20 | 3 | 66
15 | 1 | Core Persistence module - Experiment- Design- Implement |  |  | 61 | 8 |  | 74
15 | 2 | Core Cache module - Experiment- Design- Implement |  |  | 66 | 8
15 | 4 | Verification plan - V1 |  |  | 20 | 3
15 | 3 | Core Logging/auditing module - Experiment- Design- Implement | Week4 | Week4 | 75 | 9 | 94 | 94
16 | 1 | Component level performance verification for persitance and connector | Week5 | Week5 | 60 | 8 | 102 | 102
17 | 1 | Core platform development and defect fixes |  |  | 30 | 4 | 106
17 | 2 | Service API/ ADR service and EI Event |  |  | 70 | 9 |  | 115
17 | 3 | Protocol Gateway APIand XMPP Gateway | Week 6&7 | Week 6&7 | 90 | 11 | 126
18 | 1 | Persistence Tier Stub |  |  | 50 | 6
18 | 2 | Dispatcher Stub | Week8 | Week8 | 46 | 6 | 138 | 138
19 | 1 | Test infrastructure for Performance |  |  | 50 | 6 |  | 144
19 | 2 | Verification - Performance |  |  | 40 | 5 |  | 149
19 | 1 | Test infrastructure for Scalability | Week9 |  | 50 | 6
19 | 2 | Verification - Scalability | Week10 | Week9 | 40 | 5 | 160
20 | 3 | HTTP Gateway | Week11 | Week10 | 50 | 6 | 166
22 | 1 | Design and Implementation Revision | Week11 |  | 100
21 | 4 | AMQP Gateway |  |  | 50 | 6
21 | 5 | Design refinement | Week11 | Week11 | 55 | 7 | 126
22 | 4 | Verification - All systemic properties |  |  | 100
21 | 4 | Verification plan - V2 |  |  | 40 | 5
22 | 2 | Test infrastructure for rest of systemic properties | Week12 | Week12 | 30 | 4 | 128
20 | 2 | Additional service implementation |  |  | 40 | 5
|  | Week | Planned EV | Actual EV
|  | 0 | 0 | 0
|  | 1 | 3 | 3
|  | 2 | 5 | 5
|  | 3 | 9 | 7
|  | 4 | 13 | 10
|  | 5 | 14 | 13
|  | 6 | 15 | 14
|  | 7 | 17 | 16
|  | 8 | 19 | 19
|  | 9 | 23 | 20
|  | 10 | 25 | 21
|  | 11 | 25 | 22
|  | 12 | 25 | 24
|  | Week | Planned EV | Actual EV
|  | 0 | 0 | 0
|  | 1 | 21 | 21
|  | 2 | 49 | 49
|  | 3 | 66 | 60
|  | 4 | 94 | 74
|  | 5 | 102 | 94
|  | 6 | 106 | 102
|  | 7 | 126 | 115
|  | 8 | 138 | 138
|  | 9 | 160 | 144
|  | 10 | 171 | 149
|  | 11 | 184
|  | 12 | 193
Note on C19: tharanga gamaethige: Have all fail-stop mechanisms, designs, exception and error handling mechanisms

## EV Old
Legend | Not started | InProgress - Missed deadlines | InProgress - Current | Completed
Iteration | Work package # | Work Package | Expected Completion Week | Actual Completion Week | Estimate (man hours) | ONE WEEK | 161 | TWO WEEKS | 322
12 | 1 | Tools and Infrastrcture |  |  | 35
12 | 3 | Security design and Exp. |  |  | 42
12 | 2 | Protocol Ext. Exp. | Week 1 | Week 1 | 94
13 | 1 | AWS training |  |  | 30
13 | 2 | Database design and implement | Week2 | Week2 | 190
14 | 1 | Creating Solution According to the static architecture |  |  | 35
14 | 2 | Core Connector module - Experiment- Design- Implement |  |  | 56
14 | 3 | Core Message module - Experiment- Design- Implement |  |  | 26
14 | 4 | QA Tools | Week3 | Week3 | 20 | 137
15 | 1 | Core Persistence module - Experiment- Design- Implement |  |  | 61
15 | 2 | Core Cache module - Experiment- Design- Implement |  |  | 66
15 | 4 | Verification plan - V1 |  |  | 20
15 | 3 | Core Logging/auditing module - Experiment- Design- Implement | Week4 | Week4 | 75 | 147
16 | 1 | Component level performance verification for persitance and connector |  |  | 60
16 | 2 | Core HA module - Basic fail stop & Config module |  |  | 30
16 | 3 | Performance Exp. |  |  | 25
16 | 4 | Scalability Exp. Algo | Week5 | Week5 | 25 | 140
17 | 1 | Receiver Stub |  |  | 46
17 | 2 | Service API Stub Design |  |  | 20
17 | 3 | Dispatcher Stub |  |  | 50
17 | 4 | ADR service stub | Week6 | Week6 | 50 | 166
18 | 1 | Protocol Gateway API Design and Implement |  |  | 40
18 | 1 | XMPP Gateway |  |  | 50
18 | 3 | Persistence Tier Stub | Week7 | Week7 | 50 | 140
19 | 1 | Test infrastructure for Performance and Scalability |  |  | 50
19 | 2 | Verification - Performance and Scalability |  |  | 40
19 | 3 | Scalability Design Rev. | Week8 |  | 60 | 150
20 | 1 | Design refinement |  |  | 15
20 | 2 | HTTP Gateway |  |  | 50
20 | 3 | AMQP Gateway |  |  | 50
20 | 4 | Verification plan - V2 | Week9 |  | 40 | 155
21 | 1 | Core HA module - Experiment- Design- Implement |  |  | 20
21 | 2 | Test infrastructure for rest of systemic properties |  |  | 30
21 | 3 | Service API Stub Implement |  |  | 40
21 | 4 | Verification - All systemic properties | Week10 |  | 100 | 190
22 | 1 | Design and Implementation Revision | Week11 |  | 100 | 100
Week
|  | 0 | Planned EV | Actual EV
|  | 0 | 0 | 0
|  | 1 | 3 | 3
|  | 2 | 5 | 5
|  | 3 | 9 | 7
|  | 4 | 13 | 10
|  | 5 | 17
|  | 6 | 21
|  | 7 | 24
|  | 8 | 27
|  | 9 | 31
|  | 10 | 35
|  | 11 | 36
Note on C19: tharanga gamaethige: Have all fail-stop mechanisms, designs, exception and error handling mechanisms