## Itertion12
Work Package | Task | Danny | Matt | Sid | Tharanga | Best case | Most likely | Worst case | Estimate
Tooling and Infrastructure | Implement SCMP as defined by May 2012 | 6 | 2.5 | 3 | 10 | 2.5 | 5.375 | 10 | 5.6667
| Setup eclipse IDE-Indigo/ AWS SDK/ Git plug-in | 7.5 | 5 | 25 | 25 | 5 | 15.625 | 25 | 15.4167
| Define metrics and measurements for Summer | 7.5 | 8.5 | 12 | 6.5 | 6.5 | 8.625 | 12 | 8.8333
| Create the ETVX Checklist/ Requirements review Checklist and update process metrics | 3.5 | 1.5 | 2 | 2 | 1.5 | 2.25 | 3.5 | 2.3333
| Create the defect classification scheme (ODC) | 2 | 3 | 1.5 | 3 | 1.5 | 2.375 | 3 | 2.3333
34.5833
Protocol Extensibility Experiment | Interface design of protocol gateway API for experimentation | 12 | 15 | 12.5 | 20 | 12 | 14.875 | 20 | 15.25
| Implement protocol gateway API with stub code | 8 | 10 | 4 | 16 | 4 | 9.5 | 16 | 9.6667
| Design and implement ADR message/ Common message format | 12 | 8 | 14 | 9 | 8 | 10.75 | 14 | 10.8333
| Implement and test AMQP gateway for pub/sub | 12 | 14 | 12 | 20 | 12 | 14.5 | 20 | 15
| Implement and test HTTP gateway for push/pull (request/reply) | 8 | 10 | 8 | 12 | 8 | 9.5 | 12 | 9.6667
| Implement and test XMPP gateway for point-to-point | 12 | 12 | 16 | 16 | 12 | 14 | 16 | 14
| Address protocol extensibility issues in the GitHub | 5 | 5 | 3 | 6 | 3 | 4.75 | 6 | 4.6667
| Update protocol extensibility design in the ADD | 12 | 11 | 20 | 16 | 11 | 14.75 | 20 | 15
94.0833
Security Design | Identify SASL compatibility of HTTP | 6 | 2.5 | 4 | 8 | 2.5 | 5.125 | 8 | 5.1667
| Identify SASL compatibility of XMPP | 6 | 2.5 | 4 | 8 | 2.5 | 5.125 | 8 | 5.1667
| Identify SASL compatibility of AMQP | 6 | 1 | 4 | 10 | 1 | 5.25 | 10 | 5.3333
| Identify and document constraints it imposes on other TCP/IP protocols | 6 | 6 | 4 | 12 | 4 | 7 | 12 | 7.3333
| Design security module in protocol gateway API | 12 | 14 | 8 | 16 | 8 | 12.5 | 16 | 12.3333
| Update security design in ADD | 9 | 8 | 2 | 8 | 2 | 6.75 | 9 | 6.3333
41.6667
[9 empty] | 170.3333 | 170.3333
| Date | [7 empty] | Planned | Actual
| Start Date | [7 empty] | 170.33 | 170.33
| 22nd Tuesday | [7 empty] | 145.98 | 152.58
| 23rd Wednesday | [7 empty] | 121.65 | 150.25
| 24th Thursday | [7 empty] | 97.32 | 135.75 | 8.83 | 5.67
| 25th Friday | [7 empty] | 72.99 | 82 | 5.33 | 15.25 | 10.83 | 7.33 | 5.17 | 5.17 | 4.67
| 26th Saturday | [7 empty] | 48.66 | 82
| 27th Sunday | [7 empty] | 14.33 | 72
| 28th Monday | [7 empty] | 0 | 0 | 12.33 | 9.67 | 9.67 | 5 | 6.33 | 15 | 14

## Iteration13
Work Package | Task | Estimate
WP13.1 AWS Training | AWS Traning | 30
WP13.2 Database Modeling | Analyze Payloads - EI schemas | 20.3
| Analyze Message Flows | 20.4
| Identify data related to Message Flows | 11.87
| Data Analysis Meeting (2hr x5) | 10
| Create conceptual data model | 16.2
| Design Logical Data Model | 20.87
| Experiment: Data Storage Mechanism | 14.27
| Design Physical Data Model | 17.97
| Total | 161.88
| Date | Planned | Actual
| Start Date | 161.88 | 161.88
| 29th Tuesday | 138.74 | 130.88
| 30th Wednesday | 115.6 | 130.88
| 31st Thursday | 92.46 | 89.88 | 4 | 6.5 | 4 | 6.5 | 5 | 5 | 5 | 5
| 1st Friday | 69.32 | 67.18 | 10 | 3.7 | 3 | 3 | 3
| 2nd Saturday | 46.18 | 67.18
| 3rd Sunday | 23.04 | 67.18
| 4th Monday | 0 | 31.98 | 14.3 | 20.9

## Iteration14
ID | Done? | Work Package | Task | Danny | Matt | Rui | Sid | Tharanga | Best case | Most likely | Worst case | Task Estimate | Task Actual (Decimal) | Task Actual (H:M:S) | WP Estimate
WP14.1.1 | 1 | Solution Design | Team discusses solution and SCM for RI and creates solution [Detailed Design] | 15 | 14.5 | 10 | 15 | 20 | 10 | 14.9 | 20 | 14.93 | 0 | 0:00
WP14.1.2 |  |  | Create project and build script [Implementation] | 5 | 8.5 | 5 | 7 | 6 | 5 | 6.3 | 8.5 | 6.45 | 0 | 0:00
WP14.1.3 |  |  | Update SCM with discussion details [Overhead] | 3 | 4 | 4 | 4.5 | 8 | 3 | 4.7 | 8 | 4.97 | 0 | 0:00
WP14.1.4 |  |  | Setup and configure build server and build scripts [Overhead] | 8 | 12 | 4 | 10 | 12 | 4 | 9.2 | 12 | 8.8 | 0 | 0:00
35.15
WP14.2.1 | 1 | Connector Module | Internal queueing experiment [Experiment] | 20 | 21.6 | 25 | 10 | 20 | 10 | 19.32 | 25 | 18.71 | 0 | 0:00
WP14.2.2 |  |  | Design connector API (queue-abstraction) [Detailed Design] | 12 | 14.4 | 10 | 9 | 6 | 6 | 10.28 | 14.4 | 10.25 | 0 | 0:00
WP14.2.3 |  |  | Implement connector API [Implementation] | 8 | 16 | 6 | 9 | 4 | 4 | 8.6 | 16 | 9.07 | 0 | 0:00
WP14.2.4 |  |  | Implement tech-specific connector [Implementation] | 10 | 11 | 10 | 12 | 16 | 10 | 11.8 | 16 | 12.2 | 0 | 0:00
WP14.2.5 |  |  | Unit testing [QA] | 6 | 9 | 5 | 3.5 | 4 | 3.5 | 5.5 | 9 | 5.75 | 0 | 0:00
55.98
WP14.3.1 | 1 | Message Module | Evaluate suitable serialization frameworks [Arch Design] | 15 | 16 | 5 | 5 | 6 | 5 | 9.4 | 16 | 9.77 | 0 | 0:00
WP14.3.2 | 1 |  | Design message module [Detailed Design] | 6 | 9 | 5 | 4 | 6 | 4 | 6 | 9 | 6.17 | 0 | 0:00
WP14.3.3 |  |  | Implement message module [Implementation] | 4 | 4.5 | 5 | 5 | 10 | 4 | 5.7 | 10 | 6.13 | 0 | 0:00
WP14.3.4 |  |  | Unit testing [QA] | 4 | 6.5 | 4 | 3.5 | 3 | 3 | 4.2 | 6.5 | 4.38 | 0 | 0:00
26.45
WP14.5.1 |  | Cache Module | Experiment: Caching mechanism | 15 | 12 | 20 | 6.5 | 12 | 6.5 | 13.1 | 20 | 13.15 | 0 | 0:00
13.15
WP14.6.1 | 1 | QA Tools | Coding standards document for Java [Overhead] | 12 | 2.5 | 2 | 3 | 6 | 2 | 5.1 | 12 | 5.73 | 0 | 0:00
WP14.6.2 | 1 |  | Design review checklist [Overhead] | 4 | 2 | 5 | 3 | 6 | 2 | 4 | 6 | 4 | 0 | 0:00
WP14.6.3 | 1 |  | Design Review (Connector and message) [QA] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0:00 | 19.73
150.46
[15 empty] | Date | Planned | Actual
[15 empty] | Start Date | 150.46 | 150.46
[15 empty] | 5th Tuesday | 128.97 | 144.73 | 5.73
[15 empty] | 6th Wednesday | 107.48 | 120.03 | 14.93 | 9.77
[15 empty] | 7st Thursday | 85.99 | 81.15 | 18.71 | 4 | 6.17 | 10
[15 empty] | 8th Friday | 64.5 | 70.9 | 10.25
[15 empty] | 9th Saturday | 43.01 | 70.9
[15 empty] | 10th Sunday | 21.52 | 70.9
[15 empty] | 11th Monday | 0 | 21 | 9.07 | 6.13 | 4.97 | 13.15 | 5.75 | 4.38 | 6.45

## Iteration15
ID | Done? | Work Package | Tag | Task | Danny | Matt | Rui | Sid | Tharanga | Best Case | Most Likely | Worst Case | Estimate (Decimal)
WP15.1 | OPEN | Persistence Module
WP15.1.1 |  |  | Detailed Design | Design Datamodel abstraction: CRUD DTOs | 8 | 7.5 | 12 | 7.5 | 10 | 7.5 | 9 | 12 | 9.25
WP15.1.2 |  |  | Detailed Design | Design Datamodel abstraction: DTOs | 4 | 6 | 6 | 9 | 5 | 4 | 6 | 9 | 6.17
WP15.1.3 |  |  | Implementation | Implement data access abstraction layer | 11 | 15.5 | 10 | 9 | 10 | 9 | 11.1 | 15.5 | 11.48
WP15.1.4 |  |  | Implementation | Implement tech-specific | 6 | 9.5 | 5 | 6.5 | 15 | 5 | 8.4 | 15 | 8.93
WP15.1.5 |  |  | Quality Assurance | Unit Testing | 8 | 7.5 | 3 | 5.5 | 8 | 3 | 6.4 | 8 | 6.1
WP15.2 | OPEN | Cache Module
WP15.2.1 |  |  | Architecture Design | Analysis; Where is caching needed and what needs to be cached. Caching policy. Integration w/ persistence, connector | 14 | 12 | 8 | 12 | 12 | 8 | 11.6 | 14 | 11.4
WP15.2.2 |  |  | Detailed Design | Analyze the need of abstraction layer | 2 | 2.5 | 2 | 3.5 | 3 | 2 | 2.6 | 3.5 | 2.65
WP15.2.3 |  |  | Implementation | Implement selected caching mechanism into the persistence module | 16 | 9.5 | 10 | 5.5 | 10 | 5.5 | 10.2 | 16 | 10.38
WP15.2.4 |  |  | Implementation | Set up memcahed cluster on AWS | 8 | 4 | 2 | 3 | 6 | 2 | 4.6 | 8 | 4.73
WP15.2.5 |  |  | Quality Assurance | Unit testing | 4 | 5.5 | 3 | 4.5 | 5 | 3 | 4.4 | 5.5 | 4.35
WP15.3 | OPEN | State Module
WP15.3.1 |  |  | Experiments | Analysis of need of state persistence | 3 | 4 | 6 | 4.5 | 4 | 3 | 4.3 | 6 | 4.37
WP15.3.2 |  |  | Experiments | Research on shared-nothing vs. out-of-process state persistence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP15.3.3 |  |  | Experiments | Experiment to select a specific technology/ mechanism | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP15.3.4 |  |  | Detailed Design | Design of the module | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP15.3.5 |  |  | Implementation | Implementation of framework | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP15.3.6 |  |  | Implementation | Implementation of tech-specific part | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP15.3.7 |  |  | Quality Assurance | Unit Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP15.4 | OPEN | Verification Plan
WP15.4.1 |  |  | Quality Assurance | Create high-level verification plan | 12 | 4 | 5 | 5.5 | 5 | 4 | 6.3 | 12 | 6.87
WP15.4.2 |  |  | Quality Assurance | Team review of verification plan | 7.5 | 7.5 | 5 | 7.5 | 10 | 5 | 7.5 | 10 | 7.5
WP15.4.3 |  |  | Overhead | Correlate verification plan with plan of summer | 3 | 3 | 3 | 4 | 2 | 2 | 3 | 4 | 3
WP15.4.4 |  |  | Quality Assurance | Elaborate on first two verification steps | 3 | 3.5 | 5 | 3.5 | 4 | 3 | 3.8 | 5 | 3.87
WP15.5 | OPEN | Core Logging/auditing module
WP15.5.1 |  |  | Experiment | Experimentation of suitable logging technology for stateless applications | 4 | 4.5 | 5 | 5.5 | 5 | 4 | 4.8 | 5.5 | 4.78
WP15.5.2 |  |  | Detailed Design | Analyze what need to be logged/ audited | 12 | 5 | 5 | 6.5 | 7 | 5 | 7.1 | 12 | 7.57
WP15.5.3 |  |  | Detailed Design | Detail design of the logging module | 3 | 5 | 5 | 5 | 8 | 3 | 5.2 | 8 | 5.3
WP15.5.4 |  |  | Implementation | Configuration of selected logging technology into the solution | 3 | 3 | 2 | 4 | 5 | 2 | 3.4 | 5 | 3.43
WP15.6 | OPEN | QA
WP15.6.1 |  |  | Quality Assurance | Design Review (Cache, persistence and logging) | 10 | 10 | 15 | 15 | 15 | 10 | 13 | 15 | 12.83
WP14.2 | OPEN | Core - Connector
WP14.2.6 |  |  | Implementation | Rabbit instance in AWS | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
WP14.2.7 |  |  | Quality Assurance | Make generic unit test cases | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
142.96
[14 empty] | Date | Planned | Actual
[14 empty] | Start Date | 146.96 | 146.96
[14 empty] | 12th Tuesday | 125.9657 | 143.96 | 3
[14 empty] | 13th Wednesday | 104.9714 | 141.96 | 2
[14 empty] | 14th Thursday | 83.9771 | 102.79 | 6.87 | 7.5 | 1 | 1 | 9.25 | 6.17 | 2.65 | 4.73
[14 empty] | 15th Friday | 62.9829 | 83.31 | 11.48 | 3 | 5
[14 empty] | 16th Saturday | 41.9886 | 83.31
[14 empty] | 17th Sunday | 20.9943 | 71.91 | 11.4
[14 empty] | 18th Monday | 0.0042857 | 37.39 | 4.78 | 8.93 | 4.37 | 7.57 | 1 | 4 | 3.87
Note on N37: tharanga gamaethige: We kept 10 hours of buffer for rework

## Iteration17
ID | Estimate (Decimal)
WP17.1 | 92.9
WP17.1.1 | 4.17
WP17.1.2 | 6.83
WP17.1.3 | 3
WP17.1.4 | 10.33
WP17.1.5 | 10.38
WP17.1.6 | 4.35
WP17.1.7 | 3.33
WP17.1.8 | 4
WP17.1.9 | 5
WP17.1.10 | 4.67
WP17.1.11 | 5
WP17.1.12 | 20
WP17.1.13 | 11.83
WP17.2 | 68.08
WP17.2.1 | 5.67
WP17.2.2 | 6.42
WP17.2.3 | 5.5
WP17.2.4 | 5
WP17.2.5 | 5.17
WP17.2.6 | 7.42
WP17.2.7 | 7
WP17.2.8 | 4.08
WP17.2.9 | 9 |  |  |  |  | 7.05
WP17.2.10 | 5.17 |  |  |  |  | 4.15
WP17.2.11 | 7.67 |  |  |  |  | 3.87
WP17.3 | 74.88 |  |  |  |  | 6.83
WP17.3.1 | 7.68 |  |  |  |  | 7.05
WP17.3.2 | 4.72 |  |  |  | 3.33 | 7.42
WP17.3.3 | 9.3 |  |  |  | 4.17 | 5.17
WP17.3.4 | 3.93 |  |  |  | 5 | 5
WP17.3.5 | 5 |  |  |  | 4.72 | 5
WP17.3.6 | 4.15 |  |  |  | 10.33 | 7
WP17.3.7 | 7.05 |  |  |  | 5 | 9.3
WP17.3.8 | 4.53 |  |  |  |  | 3.93
WP17.3.9 | 3.87 |  |  |  | 32.55 | 71.77
WP17.3.10 | 3.37
WP17.3.11 | 5
WP17.3.12 | 7.68
WP17.3.13 | 8.6
|  | Date | Planned | Actual
|  | Start Date | 236 | 236
|  | 26th Tuesday | 216.3333 | 236
|  | 27th Wednesday | 196.6667 | 224.17 | 11.83
|  | 28th Thursday | 177 | 224.17
|  | 29th Friday | 157.3333 | 224.17
|  | 30th Saturday | 137.6667 | 212.25 | 6.42 | 5.5
|  | 1st Sunday | 118 | 212.25
|  | 2nd Monday | 98.3333 | 160.47 | 3 | 9.3 | 10.33 | 5 | 4.72 | 4.17 | 5 | 3.33 | 3 | 3.93
|  | 3rd Tuesday | 78.6667 | 150.94 | 4.53 | 5
|  | 4th Wednesday | 59 | 150.94
|  | 5th Thursday | 39.3333 | 146.86 | 4.08
|  | 6th Friday | 19.6667 | 66.12 | 7.05 | 7 | 20 | 7.42 | 5 | 5 | 5.17 | 4 | 6.83 | 4.67 | 8.6
|  | 7th Saturday | 2.1316e-14 | 50.43 | 7.67 | 3.87 | 4.15
|  | 8th Sunday | 0 | 50.43
|  | 9th Monday | 0 | 18.98 | 10.38 | 4.35 | 5.67 | 3.37 | 7.68

## Iteration 18
ID | Estimate (Decimal)
WP18.1
WP18.1.1 | 10.93
WP18.1.2 | 10.38
WP18.1.3 | 4.35
WP18.1.4 | 5
WP18.2
WP18.2.1 | 5.93
WP18.2.2 | 5
WP18.2.3 | 5.65
WP18.2.4 | 5.88
WP18.2.5 | 5.53
WP18.4
WP18.4.1 | 13.13
WP18.4.2 | 5.73
WP18.4.3 | 5
WP18.4.4 | 7.43
WP18.4.5 | 6.15
WP18.4.6 | 6.7
WP18.4.7 | 3.57
|  | Date | Planned | Actual
|  | Start Date | 106.36 | 106.36
|  | 11th Wednesday | 79.77 | 95.43 | 5.93 | 5
|  | 12th Thursday | 53.18 | 84.7 | 5.73 | 5
|  | 13th Friday | 26.59 | 68.05 | 5.65 | 7.43 | 3.57
|  | 14th Saturday | 0 | 38.99 | 10.93 | 5 | 13.13
|  | 16th Monday | 0 | 6.15 | 10.38 | 4.35 | 5.88 | 5.53 | 6.7
|  | 17th Tuesday | 0 | 0 | 6.15

## Iteration19
ID | Estimate (Decimal)
WP19.1.1 | 2
WP19.1.2 | 8.07
WP19.1.3 | 6.9
WP19.1.4 | 7.97
WP19.1.5 | 7.7
WP19.1.6 | 4.43
WP19.1.7 | 4
WP19.1.8 | 32.17
WP19.1.9 | 36.43
WP19.1.10 | 5.43
WP19.1.11 | 4.57
WP19.1.14 | 13.25
WP19.1.15 | 15
147.92
WP19.1.12 | 10.28
WP19.1.13 | 8.1
|  | Date | Planned | Actual
|  | Start Date | 147.92 | 147.92
|  | 18th Wednesday | 110.94 | 112.85 | 8.07 | 6.9 | 7.97 | 7.7 | 4.43
|  | 19th Thursday | 73.96 | 104.28 | 4 | 4.57
|  | 20th Friday | 36.98 | 89.28 | 15
|  | 21st Saturday | 0 | 89.28
|  | 23rd Monday | 0 | 47.42 | 36.43 | 5.43
|  | 24th Tuesday | 0 | 47.42

## Iteration20
ID | Estimate (Decimal)
WP20.1.1 | 5.33
WP20.1.2 | 4.67
WP20.1.3 | 5.67
WP20.1.4 | 4.17
WP20.1.5 | 3.58
WP20.1.6 | 5.58
WP20.1.7 | 3.33
WP20.2.1 | 2.75
WP20.2.2 | 1.92
WP20.2.3 | 4.33
WP20.2.4 | 6.33
WP20.2.5 | 11
WP20.2.6 | 2.33
WP20.2.7 | 2
WP20.2.8 | 6.17
WP20.2.10 | 3
WP20.3.1 | 8.75
WP20.3.2 | 8.88
WP20.3.3 | 6.67 | Date | Planned | Actual
| 96.46 | Start Date | 96.46 | 96.46
|  | 25th Wednesday | 72.345 | 89.29 | 4.17 | 3
|  | 26th Thursday | 48.23 | 74.37 | 5.58 | 2.75 | 4.67 | 1.92
|  | 27th Friday | 24.115 | 46.8 | 2 | 2.33 | 4.33 | 6.33 | 3.58 | 5.67 | 3.33
|  | 28th Saturday | 0 | 40.63 | 6.17
|  | 30th Monday | 0 | 0 | 11 | 5.33 | 8.75 | 8.88 | 6.67