## Summary
| Project Name | Argonauts-EnerNOC |  | Planned Start |  | 2012-01-17
Schedules | Project Manager | Siddharth |  | Planned End |  | 2012-02-11
Risks
Issues | Activity Summary as on | 2012-02-12 19:27
| Objectives/Primary Tasks | Estimated Effort (PH) | Planned Start | Planned End | Actual Effort So far(PH) | Remaining Effort | Effort Variance %
| Overhead & Recurring | 52 |  |  | 52.44
| QAW/ADS Workshop | 64.6667 |  |  | 66.85
| Finalize Protocols | 4.0833 |  |  | 7
| Baseline ADS | 59.4167 |  |  | 56.56
| Establishment of Metrics | 14.4167 |  |  | 9.75
| Unplanned Tasks |  |  |  | 31.23
| Total Effort | 194.5833 |  |  | 223.83
Risk Summary
| Period Ending | # Identified | # Mitigated | Retired | #Cont Executed | Monitor
Total
Issues List
| Period Ending | # Identified | Open | Closed
Iteration 5 Summary

## Schedule
Schedule
| WBS | Task / Activity | Outcome/Exit Criteria | Tags | Status | Estimated Effort (PH) | Best | Most Likely | Worst | Planned Start | Planned End | Actual Effort | Actual Start | Actual End | Resource | Expected Work Completion (%) | Actual Work Completion (%) | Effort Variance %
2 | 1.0 | Overhead & Recurring |  |  |  | 52 | NA | NA | NA | NA | NA | 52.44
| 6 | Preparation for Status Meetings |  | Operations & Process | Recurring | 6 | NA | NA | NA | NA | NA | 2.35 |  |  | Sid,Rui
|  | Status meeting |  | Operations & Process | Recurring | 20 | NA | NA | NA | NA | NA | 14.75 |  |  | Team
|  | Client Bi-weekly call |  | Client | Recurring | 10 | NA | NA | NA | NA | NA | NA |  |  | Team
|  | Mentor meeting |  | Operations & Process | Recurring | 10 | NA | NA | NA | NA | NA | 8.41 |  |  | Team |  | 0%
|  | Client communication |  | Client | Recurring | 2 | NA | NA | NA | NA | NA | 0.58 |  |  | Rui
|  | Iteration Planning Meeting |  | Planning | Recurring | NA | NA | NA | NA | NA | NA | 21 |  |  | Team |  | 0%
| 0 | Recording Time |  | Planning | Recurring | 2 | NA | NA | NA | NA | NA | 1.6 |  |  | Sid |  | 0%
|  | Update Master Design Plan |  | Planning | Recurring | NA | NA | NA | NA | NA | NA | 3.75 |  |  | Sid
|  | Metrics collection |  | Operations & Process | Recurring | 2 | NA | NA | NA | NA | NA | NA |  |  | Tharanga |  | 0%
|  | Iteration Closing & Reflection Meeting |  | Operations & Process | Recurring | NA | NA | NA | NA | NA | NA |  |  |  | Team |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
1.1.1
| 1.2 | QAW/ADW |  |  |  | 64.6667 | [5 empty] | 66.85
|  | Workshop planning meeting | Draft Agenda | Requirement Analysis/Stabilization | Done | 7.5 | 5 | 7.5 | 10 | 2012-01-20 | 2012-01-20 | 7.75 |  |  | Team
|  | Prepartion for the workshop planning meeting | Read QAW paper,Read ADW part of ACDM | Requirement Analysis/Stabilization | Done | 3.75 | 5 | 2.5 | 7.5 | 2012-01-20 | 2012-01-20 | 1.3 |  |  | Team |  | 0%
|  | Understanding intial stages of ACDM | Read stage 1 and stage 2 of the ACDM book | Operations & Process | Done | NA | NA | NA | NA | 2012-01-19 | 2012-01-20 | 8.75 |  |  | Team
|  | Understanding responsibilities as prescribed by ACDM | Read individual responsibilities section from the ACDM book | Operations & Process | Done | NA | NA | NA | NA | 2012-01-19 | 2012-01-19 | 1.5 |  |  | Team
|  | Plan logistics for workshop | Food, Rooms | Requirement Analysis/Stabilization | Done | 1.5 | 1 | 1.5 | 2 | 2012-01-27 | 2012-02-01 | 1.3 |  |  | Matt |  | 0%
| 1.25 | Workshop Communication | Agenda, emailing etc | Requirement Analysis/Stabilization | Done | 1.9167 | 1 | 2 | 2.5 | 2012-01-23 | 2012-02-01 | 1.25 |  |  | Rui |  | 0%
|  | Prepare Materials for the Workshop | Slides | Requirement Analysis/Stabilization | Done | 5 | 4 | 5 | 6 | 2012-01-31 | 2012-02-01 | 6.25 |  |  | Team |  | 0%
|  | QAW/ADW session on 2nd & 3rd Feb |  | Requirement Analysis/Stabilization | Done | 45 | 40 | 45 | 50 | 2012-02-02 | 2012-02-03 | 38.75 |  |  | Team |  | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
[6 empty] | 0 | [10 empty] | 0%
0
0
| 1.1.2 |  |  |  |  | 0 | [7 empty] | 0 |  |  |  | 0%
| 2 | Finalize Protocols |  |  |  | 4.0833 | [5 empty] | 7 | [5 empty] | 71.43%
| 2.1 | Write rationale for finalizing the 3 protocols | 1-page executive summary | Requirement Analysis/Stabilization | Done | 4.0833 | 3 | 4 | 5.5 | 2012-01-24 | 2012-01-28 | 7 | 0 | 0 | Matt |  |  | 71.43%
[6 empty] | 0 | [7 empty] | 0 |  |  |  | 0%
[6 empty] | 0 | [7 empty] | 0 |  |  |  | 0%
[6 empty] | 0 | [7 empty] | 0 |  |  |  | 0%
| 2.1.2 |  |  |  |  | 0 | [7 empty] | 0 |  |  |  | 0%
[6 empty] | 0 | [7 empty] | 0 |  |  |  | 0%
| 2.2 |  |  |  |  | 0 | [11 empty] | 0%
[6 empty] | 0 | [7 empty] | 0 |  |  |  | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
| 2.2.1 |  |  |  |  | 0 | [11 empty] | 0%
| 2.3 |  |  |  |  | 0 | [11 empty] | 0%
| 2.3.1 |  |  |  |  | 0 | [11 empty] | 0%
|  | Baseline ADS |  |  |  | 59.4167 | [5 empty] | 56.56 | [5 empty] | -4.808%
|  | Analyze technical/business constraints | Clarified format | Requirement Analysis/Stabilization | Done | 4.3333 | 3 | 4 | 7 | 2012-01-29 | 2012-01-31 | 1.25 |  |  | Sid,Tharanga |  |  | -71.15%
| 2.4 | Analyze operational descriptions | Use Case | Requirement Analysis/Stabilization | Done | 18 | 12 | 18 | 24 | 2012-01-26 | 2012-01-31 | 12.1 | 0 |  | Dan,Rui |  |  | -32.78%
| 2.4.1 | Analyze performance | 6 part scenario | Requirement Analysis/Stabilization | Done | 3.1667 | 2 | 3 | 5 | 2012-01-29 | 2012-01-31 |  |  |  | Tharanga |  |  | 0%
|  | Analyze scalability | 6 part scenario | Requirement Analysis/Stabilization | Done | 3.1667 | 2 | 3 | 5 | 2012-01-27 | 2012-01-31 | 2 |  |  | Matt |  |  | -36.84%
| 2.4.2 | Analyze modifiability | 6 part scenario | Requirement Analysis/Stabilization | Done | 4.1667 | 3 | 4 | 6 | 2012-01-29 | 2012-01-31 | 1.05 |  |  | Dan |  |  | -74.8%
|  | Review the slides (prior to workshop) | Revesion of slides | Requirement Analysis/Stabilization | Done | 7.5 | 5 | 7.5 | 10 | 2012-02-01 | 2012-02-01 | 9.16 |  |  | Team |  | 0%
|  | Analyze/Revise architectural drivers | Revision Inputs | Requirement Analysis/Stabilization | Done | 7.5 | 6 | 7.5 | 9 | 2012-02-04 | 2012-02-07 | 13.25 |  |  | Sid,Matt |  |  | 76.67%
|  | Create ADS skeleton with sections | Outline of ADS | Requirement Analysis/Stabilization | Done | 2.0833 | 1 | 2 | 3.5 | 2012-01-28 | 2012-01-31 | 1 |  |  | Matt |  |  | -52%
|  | Assemble architectural drivers into ADS | ADS document | Requirement Analysis/Stabilization | Done | 1 | 0.5 | 1 | 1.5 | 2012-02-07 | 2012-02-08 | 1.25 |  |  | Dan |  |  | 25%
|  | Review ADS as a whole | Revision Inputs | Requirement Analysis/Stabilization | Done | 7.5 | 5 | 7.5 | 10 | 2012-02-08 | 2012-02-09 | 10 |  |  | Team |  |  | 33.33%
|  | Revise ADS | Updated ADS | Requirement Analysis/Stabilization | Done | 1 | 0.5 | 1 | 1.5 | 2012-02-09 | 2012-02-10 | 5.5 |  |  | Tharanga |  |  | 450%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
|  | Establishment of Metrics |  |  |  | 14.4167 | [5 empty] | 9.75 | [5 empty] | -32.37%
|  | Establish baseline metrics for this semester | List of metrics that can be used | Operations & Process | Done | 4 | 3 | 4 | 5 | 2012-01-24 | 2012-01-30 | 2.5 |  |  | Tharanga |  |  | -37.5%
|  | Metrics discussion meeting | Final list of metrics that should be used | Operations & Process | Done | 5.4167 | 2.5 | 5 | 10 | 2012-01-25 | 2012-01-25 | 5.25 |  |  | Team |  |  | -3.077%
|  | Implementing Metrics into the project | Forms, Spreadsheets | Operations & Process | Done | 5 | 3 | 5 | 7 | 2012-02-04 | 2012-02-07 | 2 |  |  | Tharanga |  |  | -60%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
|  | Unplanned Tasks |  |  |  | 0 | [5 empty] | 31.23 | [5 empty] | #DIV/0!
[6 empty] | 0 | [11 empty] | 0%
|  | Changing of planning and tracking tool | NA | Unplanned | Done | NA | NA | NA | NA |  |  | 3.63 |  |  | Sid |  |  | #VALUE!
|  | Goals, Roles & Responsibilities Meeting |  | Unplanned | Done | 0 | [5 empty] | 7.75 |  |  | Team |  |  | #DIV/0!
|  | Sync-Up meeting |  | Unplanned | Done | 0 | [5 empty] | 6.5 |  |  | Team |  |  | #DIV/0!
|  | Preparation of iteration 5 planning meetin |  | Unplanned | Done | 0 | [5 empty] | 1.25 |  |  | Sid |  |  | #DIV/0!
|  | Preparation for the kickoff meeting |  | Unplanned | Done | 0 | [5 empty] | 0.3 |  |  | Rui |  |  | #DIV/0!
|  | Modify roles and responsibilities |  | Unplanned | Done | 0 | [5 empty] | 0.5 |  |  | Tharanga |  |  | #DIV/0!
|  | Action Items post status meetings |  | Unplanned | Done | 0 | [5 empty] | 0.3 |  |  | Matt |  |  | #DIV/0!
|  | Making the burndown chart |  | Unplanned | Done | 0 | [5 empty] | 0.75 |  |  | Sid |  |  | #DIV/0!
|  | Meeting with felix |  | Unplanned | Done | 0 | [5 empty] | 5 |  |  | Team |  |  | #DIV/0!
|  | Capturing metrics for requirements |  | Unplanned | Done | 0 | [5 empty] | 0.5 |  |  | Dan |  |  | #DIV/0!
|  | Preparation for the first group meeting |  | Unplanned | Done | 0 | [5 empty] | 1.5 |  |  | Rui |  |  | #DIV/0!
|  | Risk mgmt. and identification |  | Unplanned | Done | 0 | [5 empty] | 1.25 |  |  | Tharanga,Rui |  |  | #DIV/0!
|  | Team problem communication with mentors |  | Unplanned | Done | 0 | [5 empty] | 0.5 |  |  | Rui |  |  | #DIV/0!
| Tool | Tool maintenance |  | Unplanned | Done | 0 | [5 empty] | 1.5 |  |  | Matt |  |  | #DIV/0!
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
[6 empty] | 0 | [11 empty] | 0%
|  | Total | [15 empty] | #DIV/0!
[19 empty] | Done | Sid
[19 empty] | In Progress | Tharanga
[19 empty] | Not Started | Dan
[19 empty] | Blocked | Rui
[19 empty] | Recurring | Matt
Team
Sid,Dan
Sid,Tharanga
Sid,Rui
Sid,Matt
Dan,Tharanga
Dan,Rui
Dan,Matt
Tharanga,Rui
Tharanga,Matt
Rui,Matt
Formulas:
Actual End = Schedule[[#This Row],[Actual Start]]+Schedule[[#This Row],[Actual Effort]]
Actual Start = MIN([Actual Start, row below]:N67)

## Risks
Risk Register
Sl No | Risk Identified Date | Risk Description | Probability % | Time Frame | Impact of Risk on |  |  | Affected Phase | Risk Exposure | Mitigation Plan |  | Risk Status | Status Date
Contingency Plan
[5 empty] | Schedule | Quality | Effort | [6 empty] | Probability of Impact |  | 2 | Risk Time Frame:
[14 empty] | Process | 75 - 100% |  | Short Term
Note on D3: Impossible - 0% Likely - 25 - 50% Very Likely - 50 - 75% Certain - 75 - 100%
Note on E3: When this risk could occur. Short Term - within a month Medium Term - 1 - 3 months Long Term - After 3 months
Note on F3: Quality - (1-5) Schedule -(1-5) Effort (Cost) - (1-5) 1-Low 5- High
Note on J3: Expoure = Impact * Probability Higher exposure is not good
Note on II5: To be Defined by the USER

## Issues
Issues / Decision Register
ID | Date Identified | Issue Description | Action Plan/Resolution | Owner | Importance | Status | Date Resolved
Note on C3: What is the issue ?
Note on D3: How do you intend to deal with this issue?
Note on E3: Who Manages this issue ?
Note on F3: 3: High 2: Medium 1: Low
Note on G3: Open Closed Cannot Resolve

## Resource Levelling
| Total Available (overhead excluded) | Total Spent(on non-estimated tasks) | Total Assigned | Total Remaining
Sid | 36 | 15.93 | 22.165 | -2.095
Matt | 40 | 9.55 | 30.83 | -0.38
Tharanga | 36 | 8.05 | 30.585 | -2.635
Rui | 36 | 9.1 | 27.17 | -0.27
Dan | 40 | 8.55 | 30.42 | 1.03
Grand Total | 121.77
Note on F4: Siddharth: This is total man hours remaining for doing tasks that are NOT overhead and recurring
Note on B11: Siddharth: This figure was computed by subtracting the sum of actual efforts of all tasks for which estimation was NOT done from 188 (i.e total available hours of all team members)

## Burndown
Dates | Planned Hours Remaining | Actual Hours Remaining
2012-01-29 | 108.6 | 108.6
2012-02-01 | 67 | 79.1
2012-02-04 | 22 | 34.1
2012-02-07 | 9.5 | 22
2012-02-10 | 0 | 0