## Product Engineering
Requirements
Requirements not stable - Functional Requirements | Reference implementation my slip
EI v 1.0 spec continues to evolve. | Won't be able to deliver all functionality
Specification does not address user interaction reqs | Won't deliver usable system
Design
We do not have a test infrustructure to demonstarte feasibility of design | Scalability cannot be assessed, architecture will not scale
No experience with large-scale systems or technical knowledge on protocol transports | won't be able to design the multi-transport architecture
Code and Unit test
No development infrustructure standardized for deployment environment | take too long to deploy on target environment deployment problems
Integration and testing
No test, integratoin environment | cannot verify systemic QA concerns
No experience in testing performance and scalability concerns | will not deliver adequate analysis to EnerNOC
Engineering specialties
N/A
Planning
No structured status report ? | The communication to team, client, and mentors is not clear. Team members do not know project status
No training program | Team members are not acquiring technical skills necessary to complete the project
Quality/working environment
Team members do not have clear quality standards | Garbage product
Team members do not regularly communicate | Iterations are chaotic and tasks are not completed

## Dev Env
Development process
Multiple artifacts are being developed and changed. No config mgt process | Implementation/design not traceable to requirements
No coding process or standards or quality assurance plan defined | Quality of software artifacts suffere and don't meet customer expectations
Team does not understand dev process (ACDM) | design, planning, takes longer and milestones begin to slip

## Program Constraints
Team members do not have design experience, tesitng methods | Architecture will not conform to customer expectations