## Slide 1: Status Meeting [35 minutes]
2011.11.14
Close action items [5 min]
Lessons Learned from Iteration 2 [5 min]
Time Metrics from Iteration 2 [5 min]
Project Status [5 min]
Process Reflection [5 min]
Mentor Minutes [5 min]
ARGONAUTS

## Slide 2: Close Action Items [5 min] - Tharanga
Close open items
ARGONAUTS

## Slide 3: Lessons Learned [5 min] - Matt
What did we learn from Iteration 2?
ARGONAUTS

## Slide 4: Lessons Learned
Good – Better clarity on tasks (Planning Poker helped)
Good – Undisturbed work progress (one “planning mtg”)
Could be Better – Threshold of success on tasks: “Done”
Could be Better – Discipline in proposing methods
  Expected outcome, measures of success
Not so Good – Resource leveling using estimates
Not so Good – Regular tracking of task progress

## Slide 5: Time Metrics for Iteration 2 [5 min] - Dandan
What did the data tell us?
ARGONAUTS

## Slide 6: Project Status [5 min] - Rui
Where are we? Where are we going?
ARGONAUTS

## Slide 7: View From Macro plan
SEP’11
OCT’11
NOV’11
DEC’11
JAN’12
FEB’12
MAR’12
Kickoff
Identify Architectural Drivers
Business Goals
EOSP
SOW
SRS
Phase 1
Architecture Refinement and Prototyping
MOSP
Notional
Architecture
Phase 2
Architectural Spike on
Multiple Protocol

## Slide 8: View From Milestones
Project Milestones – Phase 1
Milestones | Date | Description | Owner
 | Sep 23 | 1. Project Kick-off | Dev. Lead
 | Oct 28 | 2. Quality Attributes Identified | Dev. Lead
 | Nov 30 | 3. Functional Requirements Captured | Architect
 | Dec 09 | 4. SRS v1.0 Sign-off | Project Mgr.
 | Dec 09 | 5. SOW Sign-off | Team Lead
 | Dec 15 | 6. EOSP | Team Lead
1
2
3
5
4
6

## Slide 9: Last Week (10/14)
Macro plan & Milestone plan
WBS in a proper format
Capture quality attributes: Performance, scalability
Iteration 2 reflection
Client bi-weekly meeting

## Slide 10: This week (11/14) 59.39H
Iteration 3 planning (Partial done)
Create logical architecture
Client meeting on logical architecture
Template for function requirements (T)
Functional requirement capture from white paper(R) and comm logs(D) and consolidation
Update SOW (M)
Proposals (S)

## Slide 11: Process Reflection [5 min] - Sid
What are we doing?
ARGONAUTS

## Slide 12: Defining the Problem
Approach | Status | Useful? | Purpose/Outcome
Biweekly Conf. Call | ACTIVE (same) |  | Client feedback and input Captured in client comm. log
What is the problem? What does the client want and need?
ARGONAUTS

## Slide 13: Operations
Approach/Tool | Status | Useful? | Purpose/Outcome
Status Meetings | ACTIVE(same) |  | Weekly heading check
Team Fridays (or Mondays)- Team members love this! | ACTIVE (same) |  | Morale check, team better
Action-Item Register | ACTIVE(same) |  | Capture short, corrective actions
Google Docs | ACTIVE(down) |  | Configuration management Internal communication
Google Calendar | ACTIVE(same) |  | Scheduling and coordination
Github (Argo) | ACTIVE(same) |  | Shared repository w/ client
How do we formally operate and interact as a team?
ARGONAUTS

## Slide 14: Operations
Approach/Tool | Status | Useful? | Purpose/Outcome
Drop Box | ACTIVE(same) |  | Have a common place for team members to share files Co-ordination of group projects
Iteration Cycles | ACTIVE(same) |  | To let people know what they are exactly supposed to do. To improve focus To create and refine deliverables and artifacts
Daily Stand up meetings | Proposed | ? | To get an understanding of what everyone does on a daily basis. To address concerns/blocks that people face while carrying out assigned tasks
How do we formally operate and interact as a team?
ARGONAUTS

## Slide 15: Plans
Approach/Tool | Status | Useful? | Purpose/Outcome
Risk-Register | ACTIVE (same) |  | Continuous risk management
Task List | ACTIVE (same) |  | The current work plan
Planning Poker | ACTIVE (same) |  | Initial estimation and schedule
How do we manage, track, and evaluate our progress?
ARGONAUTS

## Slide 16: Design
How do we design a solution for our client’s problem?
Approach/Tool | Status | Useful? | Purpose/Outcome
ARGONAUTS

## Slide 17: Mentor Minutes [5 min]
Feedback.
ARGONAUTS