## Slide 1: Status Meeting [35 minutes]
2011.11.29
Close action items [5 min]
Configuration Mgt [5 min]
Project Status [10 min]
Process Reflection [10 min]
Mentor Minutes [5 min]
ARGONAUTS

## Slide 2: Close Action Items [5 min] - Matt
Close open issues
ARGONAUTS

## Slide 3: Configuration Mgt. [5 min] - Matt
Abandon ship!
ARGONAUTS

## Slide 4: Git Migration
Client Git Repository
  Project deliverables
  Meeting minutes for client calls
  Status reports to the client
Internal Git Repository
  Process, Reflection
  Planning, Tracking
  Operations
Easy to “Promote” stuff from Internal to Client (QA!!)

## Slide 5: Migration Go/No-Go
Item | Moves To | Format
Risk Register (G) | Internal Git | Wiki
Action Items (G) | Internal Git | Issue Tracker
Roles & Responsibilities (G) | Internal Git | Wiki
Meeting Minutes (G) | Internal Git | Wiki
Client Comm. Log (G) | Client Git | Wiki
WBS (G, Rui’s Computer) | Internal Git | Excel Document WBS Pro Document
Iteration Planning/Tracking (G) | Internal Git | Excel Documents

## Slide 6: Migration Go/No-Go
Item | Moves To | Format
Kick-Off Agenda (G) | Client Git | Word Document
Planning Proposal (G) | Internal Git | Wiki
Operations Proposal (G) | Internal Git | Wiki
Prob. Def Proposal (G) | Internal Git | Wiki
Implementation Proposal (G) | Internal Git | Wiki
Design Proposal (G) | Internal Git | Wiki
Iteration Reflections (G) | Internal Git | Word Documents
Weekly Process Reflection (G) | Internal Git | Wiki

## Slide 7: Migration Go/No-Go
Item | Moves To | Format
Status Meeting Slides (DB) | Internal Git | PPT Documents
Bootcamp Slides (All over) | Internal Git | PPT Documents
Architecture Drivers Spec | Client Git | Word Document
SOW | Client Git | Word Document
Milestone Schedule | Client Git | PPT Document
Reference Books and Papers | Internal Git | Various
Configuration Mgt Plan | Internal Git | Word Document
EOSP Fun | Internal Git | Wiki/PPT

## Slide 8: Git Migration Complete Milestone
Each item will be an “issue” on the Internal Git
We’ll track progress toward “migration complete”
Become proficient with Git
Log time spent migrating under “Config Mgt Task”

## Slide 9: Project Status [10 min] - Rui
Where are we? Where are we going?
ARGONAUTS

## Slide 10: View From Macro plan
SEP’11
OCT’11
NOV’11
DEC’11
JAN’12
FEB’12
MAR’12
Kickoff
Identify Architectural Drivers
Business Goals
EOSP
SOW
SRS
Phase 1
Architecture Refinement and Prototyping
MOSP
Notional
Architecture
Phase 2
Architectural Spike on
Multiple Protocol

## Slide 11: Iteration 3 Summary
High-level objectives:
Identify High-Level Functional Requirements(white paper part done, communication part will done today).
Prepare for EOSP
SOW(Done and a version on GIT)
Proposals(without design proposal )
ARGONAUTS

## Slide 12: Remain tasks
  Review and consolidate functional requirements
  EOSP
  Tailoring ACDM
  Configuration management plan
ARGONAUTS

## Slide 13: Process Reflection [10 min] - Sid
What are we doing?
ARGONAUTS

## Slide 14: Defining the Problem
Approach | Status | Useful? | Purpose/Outcome
Biweekly Conf. Call | ACTIVE (down) |  | Client feedback and input Captured in client comm. log
What is the problem? What does the client want and need?
ARGONAUTS

## Slide 15: Operations
Approach/Tool | Status | Useful? | Purpose/Outcome
Status Meetings | ACTIVE(same) |  | Weekly heading check
Team Fridays (or Mondays)- Team members love this! | ACTIVE (same) |  | Morale check, team better
Action-Item Register | ACTIVE(same) |  | Capture short, corrective actions
Google Docs | ACTIVE(same) |  | Configuration management Internal communication
Google Calendar | ACTIVE(same) |  | Scheduling and coordination
Github (Argo) | ACTIVE(same) |  | Shared repository w/ client
How do we formally operate and interact as a team?
ARGONAUTS

## Slide 16: Operations
Approach/Tool | Status | Useful? | Purpose/Outcome
Drop Box | ACTIVE (down) |  | Have a common place for team members to share files Co-ordination of group projects
Iteration Cycles | ACTIVE(same) |  | To let people know what they are exactly supposed to do. To improve focus To create and refine deliverables and artifacts
Daily Stand up meetings | Proposed (new) | ??? | To get an understanding of what everyone does on a daily basis. To address concerns/blocks that people face while carrying out assigned tasks
How do we formally operate and interact as a team?
ARGONAUTS

## Slide 17: Plans
Approach/Tool | Status | Useful? | Purpose/Outcome
Risk-Register | ACTIVE (same) |  | Continuous risk management
Iteration Burn down (Task List) | ACTIVE (down) |  | The current work plan
Planning Poker | ACTIVE (same) |  | Initial estimation and schedule
WBS | ACTIVE (new) |  | Overall Plan Activities to be performed to complete project
Milestone Planning | ACTIVE (new) |  | What are the milestones that need to be achieved? Planning using the milestones to be achieved!
How do we manage, track, and evaluate our progress?
ARGONAUTS

## Slide 18: Mentor Minutes [5 min]
Prevent the Argo from hitting big rocks.
ARGONAUTS