## Slide 1: Status Meeting [50 minutes]
2012.05.29
Changed Plan Of Action and Milestone Chart for Summer [5mins]-TG
Round Table [3mins]-Team
Action Items [2mins]-Sid
Project Progress [10mins]-TG
Architecture Design Updates [5mins]-Rui
Architecture Experiments Updates [5mins]-Dan
Metrics and Measurements [5mins]-Matt
Open Risks and Mitigation Strategies [5mins]-TG
Mentor Comments [10mins]-Team
ARGONAUTS

## Slide 2: Changed POA and Milestone Chart[5 min] - TG
ARGONAUTS

## Slide 3: Summer 2012 Milestones
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
May
June
July
August
September
12
15
17
16
19
20
Iterations
13
14
18
21
Infrastructure, Tools
and AWS Training
Experiments and Design revisions
Verification Plan
Architecture stub
EOSP
Architecture
Verified

## Slide 4: Changing POA for Summer
Problem
  Infeasible semester goal
  “Waterfallish”, verification at the end
Solution (To be finalized)
  Experiment –> Detail Design -> Stub implementation
  Verifying step by step

## Slide 5: Round Table[3 min] - Team
ARGONAUTS

## Slide 6: Action Items[2 min] - Sid
ARGONAUTS

## Slide 7: Project Progress[10 min] - TG
ARGONAUTS

## Slide 8: Change in the planning process
Start with couple of weekly iterations
Basecamp for both work packages and tasks
Task board for visibility and tracking
Resource leveling with less overhead

## Slide 9: Week 1 Total Time – 206 Hours

## Slide 10: Iteration 12 Burn down
Chart: 
| Start Date | 22nd Tuesday | 23rd Wednesday | 24th Thursday | 25th Friday | 26th Saturday | 27th Sunday | 28th Monday







Planned | 170.33 | 145.98 | 121.65 | 97.32 | 72.99 | 48.66 | 14.33 | 0
Actual | 170.33 | 152.58 | 150.25 | 135.75 | 82 | 82 | 72 | 0
Hours
Days

## Slide 11: Overall Progress – Summer 2012
Chart: 
| 0 | 1 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16
Planned EV | 0 | 3 | 7 | 12 | 15 | 17 | 18 | 20 | 21 | 22
Actual EV | 0 | 3
Week
Value

## Slide 12: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 13: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 14: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 15: Sustainable Pace Goal

## Slide 16: Sustainable Pace Goal
Recommendations:
  Don’t count on much collaborative work on weekends
  Plan daily targets at least one week in advance
  Front-load meetings and overhead on Mondays

## Slide 17: 30% Overhead Goal
Resource | Week-1 Overhead
Team Lead | 41%
Chief Architect | 21%
Development Lead | 31%
Planning Manager | 60%
Quality Assurance | 32%
Team | 37%

## Slide 18: 30% Overhead Goal
Week-1 Overhead Activity | Hours
WP00.1.1: Iteration 12 Planning | 23hrs
WP00.1.9: Planning and Tracking | 15hrs
WP00.1.20: Backlog/Issue Mtg. | 10hrs
WP00.1.8: Kickoff Mtg. | 8hrs
Recommendations:
  Time-box and monitor planning meeting cost
  Automate creation of task cards from Basecamp
  Streamline and identify duplication of planning/tracking effort

## Slide 19: Period of Certainty Goal
Issue Type | Open | Dominant Method
Design Defects | 27 Issues | 
Documentation Defects | 8 Issues | ADEW
Protocol Extensibility | 11 Issues | Experimentation
Availability | 10 Issues | ADEW
Performance | 8 Issues | ADEW
Scalability | 5 Issues | ADEW
Service Extensibility | 1 Issue | ADEW

## Slide 20: Open Risks and Mitigation Strategies [5 min] - TG
ARGONAUTS

## Slide 21: Top 3 Risks
System security requirement is not yet finalized
Cost of using AWS
No experience with large scale systems

## Slide 22: Mentor Comments[10 min] - Team
ARGONAUTS