## Slide 1: Status Meeting [50 minutes]
2012.06.05
Round Table [3 min]-Team
Action Items [2 min]-Sid
Project Progress [15 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [10 min]-Team
ARGONAUTS

## Slide 3: Round Table[3 min] - Team
ARGONAUTS

## Slide 4: Action Items[2 min] - Sid
ARGONAUTS

## Slide 5: Project Progress[15 min] - TG
ARGONAUTS

## Slide 6: Summer 2012 Milestones
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
May
June
July
August
September
12
15
17
16
19
20
Iterations
13
14
18
21
Infrastructure, Tools
AWS Training
Database and Core Components
Architecture Stub
Scalability and
Performance Verified
EOSP
Architecture
Verified
19
22
Protocol Gateway
Implemented
Design
Revisions

## Slide 7: Week 2 Total Time – 202.5 Hours

## Slide 8: Iteration 13 Burn down
Hours
Days
Chart: 
| Start Date | 29th Tuesday | 30th Wednesday | 31st Thursday | 1st Friday | 2nd Saturday | 3rd Sunday | 4th Monday
Planned | 161.88 | 138.74 | 115.6 | 92.46 | 69.32 | 46.18 | 23.04 | 0
Actual | 161.88 | 130.88 | 130.88 | 89.88 | 67.18 | 67.18 | 67.18 | 31.98

## Slide 9: Iteration 13
Two outstanding tasks
  Documenting conceptual data model
  Physical data model – [Iteration 14 backlog]
Why iteration was not complete?
  Few serial tasks in one big work package
  Confusion on tasks

## Slide 10: Iteration 14
Creating Solution According to the static architecture
Experiment - Design- Implementation
  Core Connector module
  Core Message module
Experiment on caching
QA Tools

## Slide 11: Changes on planning
Set 42 hours as the realistic target – 210 hours
Evaluate estimation accuracy with Planned vs. Estimated
Independent tasks in iteration backlog

## Slide 12: Overall Progress – Summer 2012
Week
Value
Chart: 
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 11 | 13
Planned EV | 0 | 3 | 5 | 9 | 12 | 14 | 17 | 22 | 27 | 29 | 31 | 33
Actual EV | 0 | 3 | 4

## Slide 13: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 14: Status
Protocol extensibility (core API)
Data model design (physical model, only relational database)
Core technologies experiments
  will last 2 iterations

## Slide 15: Issues we have
Chart: 
Issues Found | 34 | 67 | 138
Issues Fixed | 31 | 56 | 101
Issues Remaining | 3 | 11 | 37

## Slide 16: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 17: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 18: Sustainable Pace Goal – 48hrs

## Slide 19: Sustainable Pace Goal – 48hrs
Recommendation:
48 task hours per person-week is not sustainable
Plan using 42 task hours per person-week

## Slide 20: Sustainable Pace Goal – 42hrs

## Slide 21: 30% Overhead Goal
Resource | Week-1 | Week-2 | % Change
Team Lead | 41% | 24% | -42%
Chief Architect | 21% | 35% | +69%
Development Lead | 31% | 22% | -29%
Planning Manager | 60% | 47% | -22%
Quality Assurance | 32% | 33% | +2%
Team | 37% | 32% | -14%

## Slide 22: 30% Overhead Goal
Week-2 Overhead Activity | Hours
WP00.1.24: Iteration 13 Planning | 21hrs
WP00.1.5: Standup Meetings | 8.5hrs (30min / meeting)
WP00.1.9: Planning and Tracking | 7.8hrs (-48%)
Potential Issues:
  Standup meetings are exceeding 15min/meeting

## Slide 23: 30% Overhead Goal
-11%
-20%

## Slide 24: General Indicators

## Slide 25: General Indicators
QA Improvements:
ETVX criteria for tasks
Iteration Reflection

## Slide 26: Open Risks and Mitigation Strategies [5 min] - TG
ARGONAUTS

## Slide 27: Top 3 Risks
Condition | Consequence
The system security requirement is still not clear | We may need to change our arch. corresponding to the design for security, however it may have a impact on whole arch
Team will use AWS for implementation and evaluation and AWS costs money | The team may overrun its budget given by the customer
No experience with large-scale systems or technical knowledge on protocol transports | May be not able to design the multi-transport architecture

## Slide 28: Mentor Comments[10 min] - Team
ARGONAUTS