## Slide 1: Status Meeting [55 minutes]
2012.06.12
Round Table [3 min]-Team
Action Items [2 min]-Sid
Project Progress [15 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [15 min]-Team
ARGONAUTS

## Slide 2: Round Table[3 min] - Team
ARGONAUTS

## Slide 3: Action Items[2 min] - Sid
ARGONAUTS

## Slide 4: Project Progress[15 min] - TG
ARGONAUTS

## Slide 5: Iteration 14 Burn down
Hours
Days
Chart: 
| Start Date | 5th Tuesday | 6th Wednesday | 7st Thursday | 8th Friday | 9th Saturday | 10th Sunday | 11th Monday
Planned | 150.46 | 128.97 | 107.48 | 85.99 | 64.5 | 43.01 | 21.52 | 0
Actual | 150.46 | 144.73 | 120.03 | 81.15 | 70.9 | 70.9 | 70.9 | 21

## Slide 6: Week 3 Total Time – 195.5 Hours

## Slide 7: Overall Progress – Summer 2012
Week
Value
Chart: 
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 11 | 13
Planned EV | 0 | 3 | 5 | 9 | 12 | 14 | 17 | 22 | 27 | 29 | 31 | 33
Actual EV | 0 | 3 | 4 | 7

## Slide 8
Core
Layer
Module
Legend
A
B
A allowed to use B
XMPP
Gateway
Persistence
Receiver
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
StateMgt
In-Progress
Not Started
Done

## Slide 9: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 11: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 12: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 13: Sustainable Pace Goal – 42hrs
“Answer to the ultimate question of life, the universe, and everything: 42.”
Majority of work hours remaining after Friday are not used.

## Slide 14: Sustainable Pace Goal – 42hrs
“Answer to the ultimate question of life, the universe, and everything: 42.”

## Slide 15: Iteration Deficit: 20.48 hrs

## Slide 16: 30% Overhead Goal
Resource | % Overhead | Resource | % Overhead
Team Lead | 23% | Planning Manager | 42%
Chief Architect | 20% | Quality Assurance | 30%
Development Lead | 19% | Team | 26%

## Slide 17: Overhead Watchlist
Top 3 Overhead Activities
WP00.1.27: Iteration 14 Planning
WP00.1.5: Standup Meetings
WP00.1.9: Planning and Tracking

## Slide 18: Overhead Watchlist - Planning

## Slide 19: Issue Tracking

## Slide 20: Issue Tracking

## Slide 21: Open Risks and Mitigation Strategies [5 min] - TG
ARGONAUTS

## Slide 22: Mentor Comments[15 min] - Team
ARGONAUTS