## Slide 1: Status Meeting [50 minutes]
2012.06.26
Round Table [3 min]-Team
Action Items [2 min]-Sid
Project Progress [15 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [10 min]-Team
ARGONAUTS

## Slide 2: Round Table[3 min] - Team
ARGONAUTS

## Slide 3: Action Items[2 min] - Sid
ARGONAUTS

## Slide 4: Project Progress[15 min] - TG
ARGONAUTS

## Slide 5: Week 5 Total Time – 213 Hours
49H 04min
42H 34min
42H 30min
41H 29min
37H 13min

## Slide 6: Change of plan
Scope down end of summer goal – Verify only high priority quality attributes
  Scalability
  Performance
  Service Extensibility
  Protocol Extensibility
Let customer decide on Fall activities – Continue on high priority QAs vs. verify other QAs
Parallel work streams – bottom up and top down
Paired development

## Slide 7: Overall Progress – Summer 2012
Week
Value
Chart: 
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Planned EV | 0 | 3 | 5 | 9 | 13 | 14 | 16 | 17 | 20 | 22 | 25 | 27
Actual EV | 0 | 3 | 5 | 7 | 10 | 13

## Slide 8
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Receiver
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
StateMgt
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence

## Slide 9
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Receiver
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence

## Slide 10: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 11: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 12: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 13: Sustainable Pace Goal – 42hrs

## Slide 14: Sustainable Pace Goal – 42hrs

## Slide 15: Iteration Surplus: 50.3 hrs

## Slide 16: 30% Overhead Goal
Resource | % Overhead | Resource | % Overhead
Team Lead | 16% | Planning Manager | 27%
Chief Architect | 50% | Quality Assurance | 26%
Development Lead | 17% | Team | 27%

## Slide 17: Overhead Watchlist
Top 3 Overhead Activities (Non-Planning)
WP00.1.10: Tool Maintenance
WP00.1.9: Planning & Tracking
WP00.1.5 Standup Meetings

## Slide 18: Overhead Watchlist - Planning

## Slide 19: Design Defects

## Slide 20: Open Risks and Mitigation Strategies [5 min] - TG
ARGONAUTS

## Slide 21: Mentor Comments[10 min] - Team
ARGONAUTS