## Slide 1: Status Meeting [50 minutes]
2012.06.26
Round Table [3 min]-Team
Action Items [2 min]-Sid
Project Progress [15 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [10 min]-Team
ARGONAUTS

## Slide 2: Round Table[3 min] - Team
ARGONAUTS

## Slide 3: Action Items[2 min] - Sid
ARGONAUTS

## Slide 4: Project Progress[15 min] - TG
ARGONAUTS

## Slide 5: Week 4 Total Time – 220.5 Hours
52H 52min
50H
42H 52min
41H 14min
33H 28min

## Slide 6: Iteration 15 Burn down
Hours
Days
Chart: 
| Start Date | 12th Tuesday | 13th Wednesday | 14th Thursday | 15th Friday | 16th Saturday | 17th Sunday | 18th Monday
Planned | 146.96 | 125.9657 | 104.9714 | 83.9771 | 62.9829 | 41.9886 | 20.9943 | 0.0042857
Actual | 146.96 | 143.96 | 141.96 | 102.79 | 83.31 | 83.31 | 71.91 | 37.39

## Slide 7: Incomplete work packages
Four outstanding tasks
  Caching module (14 hours)
  Persistence module (6 hours)
  Logging (9 hours)
  Final review (6 hours)
Why iteration was not complete?

## Slide 8: Overall Progress – Summer 2012
Week
Value
Chart: 
| 0.0 | 0.0 | 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0 | 11.0
Planned EV | 0 | 3 | 5 | 9 | 13 | 17 | 21 | 24 | 27 | 31 | 35 | 36
Actual EV | 0 | 3 | 5 | 7 | 10

## Slide 9
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Receiver
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
StateMgt
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence

## Slide 10: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 11: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 12: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 13: Sustainable Pace Goal – 42hrs

## Slide 14: Sustainable Pace Goal – 42hrs

## Slide 15: Iteration Surplus: 50.3 hrs

## Slide 16: 30% Overhead Goal
Resource | % Overhead | Resource | % Overhead
Team Lead | 16% | Planning Manager | 27%
Chief Architect | 50% | Quality Assurance | 26%
Development Lead | 17% | Team | 27%

## Slide 17: Overhead Watchlist
Top 3 Overhead Activities (Non-Planning)
WP00.1.10: Tool Maintenance
WP00.1.9: Planning & Tracking
WP00.1.5 Standup Meetings

## Slide 18: Overhead Watchlist - Planning

## Slide 19: Design Defects

## Slide 20: Open Risks and Mitigation Strategies [5 min] - TG
ARGONAUTS

## Slide 21: Mentor Comments[15 min] - Team
ARGONAUTS