## Slide 1: Status Meeting [50 minutes]
2012.07.02
Round Table [3 min]-Team
Action Items [2 min]-Sid
Project Progress [15 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [10 min]-Team
ARGONAUTS

## Slide 2: Round Table[3 min] - Team
ARGONAUTS

## Slide 3: Action Items[2 min] - Sid
ARGONAUTS

## Slide 4: Project Progress[15 min] - TG
ARGONAUTS

## Slide 5: Iteration 16 Burn down
Chart: 
| Start Date | 26th Tuesday | 27th Wednesday | 28th Thursday | 29th Friday | 30th Saturday | 1st Sunday | 2nd Monday | 3rd Tuesday | 4th Wednesday | 5th Thursday | 6th Friday | 7th Saturday
Planned | 236 | 216.3333 | 196.6667 | 177 | 157.3333 | 137.6667 | 118 | 98.3333 | 78.6667 | 59 | 39.3333 | 19.6667 | 2.1316e-14
Actual | 236 | 236 | 224.17 | 224.17 | 224.17 | 212.25 | 212.25 | 209.25
Hours
Days

## Slide 6: Week 5 Total Time – 213 Hours
51H
44
42.5H
40
35H

## Slide 7: Overall Progress – Summer 2012
Week
Value
Chart: 
| 0.0 | 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0 | 11.0
Planned EV | 0 | 3 | 5 | 9 | 13 | 14 | 16 | 17 | 20 | 22 | 25 | 27
Actual EV | 0 | 3 | 5 | 7 | 10 | 13

## Slide 8
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Receiver
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence

## Slide 9
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Receiver
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence

## Slide 10: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 11: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 12: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 13: Sustainable Pace Goal – 42hrs

## Slide 14: Sustainable Pace Goal – 42hrs

## Slide 15: 30% Overhead Goal
Resource | % Overhead | Resource | % Overhead
Team Lead | 39% | Planning Manager | 35%
Chief Architect | 24% | Quality Assurance | 22%
Development Lead | 34% | Team | 31%

## Slide 16: Overhead Watchlist
Top 3 Overhead Activities (Non-Planning)
WP00.1.10: Tool Maintenance
WP00.1.9: Planning & Tracking
WP00.1.5 Standup Meetings

## Slide 17: Overhead Watchlist - Planning

## Slide 19: Design Defects

## Slide 21: Open Risks and Mitigation Strategies [5 min] - TG
ARGONAUTS

## Slide 22: Mentor Comments[10 min] - Team
ARGONAUTS