## Slide 1: Status Meeting [35 minutes]
2012.07.17
Round Table [5 min]-Team
Project Progress [13 min]-TG
Architecture Experiments Updates [5 min]-Dan
Mentor Comments [12 min]-Team
ARGONAUTS

## Slide 2: Round Table[5 min] - Team
ARGONAUTS

## Slide 3: Project Progress[13 min] - TG
ARGONAUTS

## Slide 4: Week 8 Total Time – 214 Hours
56H
45H 25M
42H 43M
36H 33M
33H

## Slide 5: Iteration 18 Burn down
Hours
Days
Chart: 
| Start Date | 11th Wednesday | 12th Thursday | 13th Friday | 14th Saturday | 16th Monday | 17th Tuesday
Planned | 106.36 | 79.77 | 53.18 | 26.59 | 0 | 0 | 0
Actual | 106.36 | 95.43 | 84.7 | 68.05 | 38.99 | 6.15 | 0

## Slide 6: Overall Progress – Summer 2012
Week
Value
Chart: 
Planned EV | 0 | 3 | 5 | 9 | 13 | 14 | 15 | 17 | 19 | 21 | 24 | 26 | 28
Actual EV | 0 | 3 | 5 | 7 | 10 | 13 | 14 | 16 | 19

## Slide 7
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence
Receiver

## Slide 8
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence
Receiver
Deferred

## Slide 9: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 10: Mentor Comments[12 min] - Team
ARGONAUTS