## Slide 1: Status Meeting [35 minutes]
2012.07.24
Round Table [5 min]-Team
Action Items [2 min]-Sid
Project Progress [13 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [10 min]-Team
ARGONAUTS

## Slide 2: Round Table[5 min] - Team
ARGONAUTS

## Slide 3: Action Items [2 min] - Sid
ARGONAUTS

## Slide 4: Project Progress[13 min] - TG
ARGONAUTS

## Slide 5: Week 9 Total Time – 218 Hours
47H 42M
45H 55M
42H 13M
41H 46M
41H

## Slide 6: Iteration 18 Burn down
Hours
Days
Chart: 
| Start Date | 18th Wednesday | 19th Thursday | 20th Friday | 21st Saturday | 23rd Monday | 24th Tuesday
Planned | 147.92 | 110.94 | 73.96 | 36.98 | 0 | 0 | 0
Actual | 147.92 | 112.85 | 104.28 | 89.28 | 89.28 | 47.42 | 47.42

## Slide 7: Overall Progress – Summer 2012
Week
Value
Chart: 
Planned EV | 0 | 3 | 5 | 9 | 13 | 14 | 15 | 17 | 19 | 21 | 24 | 26 | 28
Actual EV | 0 | 3 | 5 | 7 | 10 | 13 | 14 | 16 | 19 | 19

## Slide 8
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence
Receiver
Deferred

## Slide 9
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence
Receiver
Deferred

## Slide 10: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 11: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 12: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 13: Sustainable Pace Goal – 42hrs

## Slide 14: Sustainable Pace Goal – 42hrs

## Slide 15: 30% Overhead Goal
Resource | % Overhead | Resource | % Overhead
Team Lead | 12% | Planning Manager | 12%
Chief Architect | 11% | Quality Assurance | 12%
Development Lead | 11% | Team | 11%

## Slide 16: Overhead Watchlist
Top 3 Overhead Activities (Non-Planning)
WP00.1.5 Standup Meeting
WP00.1.9: Planning & Tracking

## Slide 17: Overhead Watchlist - Planning

## Slide 18: Rework Costs

## Slide 19: Open Risks and Mitigation Strategies [5 min] - Team
ARGONAUTS

## Slide 20: Mentor Comments[12 min] - Team
ARGONAUTS