## Slide 1: Status Meeting [50 minutes]
2012.07.31
Round Table [5 min]-Team
Action Items [2 min]-Sid
Project Progress [13 min]-TG
Architecture Design Updates [5 min]-Rui
Architecture Experiments Updates [5 min]-Dan
Metrics and Measurements [5 min]-Matt
Open Risks and Mitigation Strategies [5 min]-TG
Mentor Comments [10 min]-Team
ARGONAUTS

## Slide 2: Round Table[5 min] - Team
ARGONAUTS

## Slide 3: Action Items [2 min] - Sid
ARGONAUTS

## Slide 4: Project Progress[13 min] - TG
ARGONAUTS

## Slide 5: Week 10 Total Time – 208 Hours
46H 49M
45H 20M
4H 13M
40H 07M
35H

## Slide 6: Iteration 20 Burn down
Hours
Days
Chart: 
| Start Date | 25th Wednesday | 26th Thursday | 27th Friday | 28th Saturday | 30th Monday
Planned | 96.46 | 72.345 | 48.23 | 24.115 | 0 | 0
Actual | 96.46 | 89.29 | 74.37 | 46.8 | 40.63 | 0

## Slide 7: Overall Progress (point based) – Summer 2012
Week
Value
Chart: 
Planned EV | 0 | 3 | 5 | 9 | 13 | 14 | 15 | 17 | 19 | 23 | 25 | 27 | 29
Actual EV | 0 | 3 | 5 | 7 | 10 | 13 | 14 | 16 | 19 | 20 | 21

## Slide 8: Overall Progress (weight based) – Summer 2012
Week
Value
Chart: 
Planned EV | 0 | 21 | 49 | 66 | 94 | 102 | 106 | 126 | 138 | 160 | 171 | 184 | 193
Actual EV | 0 | 21 | 49 | 60 | 74 | 94 | 102 | 115 | 138 | 144 | 149

## Slide 9
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence
Receiver
Deferred

## Slide 10
Core
Layer
Module
Legend
A
B
A allowed to use B
Gateway
Dispatcher
OADR
Services
Framework
Facade
Handlers
Payloads
Connector
Persistence
Cache
Config
Log
Error
Message
Data
Gateway API
XMPP Stub
In-Progress
Not Started
Done
HTTP Stub
AMQP Stub
Persistence
Receiver
Deferred

## Slide 11: Summer 2012 Milestones
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
May
June
July
August
September
12
15
17
16
19
20
Iterations
13
14
18
21
Infrastructure, Tools
AWS Training
Database and Core Components
Architecture Stub
Scalability and
Performance Verified
EOSP
Architecture
Verified
19
22
Protocol Gateway
Implemented
Design
Revisions

## Slide 12: Where are we ?
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
May
June
July
August
September
12
15
17
16
19
20
Iterations
13
14
18
21
Infrastructure, Tools
AWS Training
Database and Core Components
Architecture Stub
Scalability and
Performance Verified
EOSP
Architecture
Verified
19
22
Protocol Gateway
Implemented

## Slide 13: Architecture Design Updates [5 min] - Rui
ARGONAUTS

## Slide 14: Architecture Experiments Updates [5 min] - Dan
ARGONAUTS

## Slide 15: Metrics and Measurements [5 min] - Matt
ARGONAUTS

## Slide 16: Sustainable Pace Goal – 42hrs

## Slide 17: Sustainable Pace Goal – 42hrs

## Slide 18: 30% Overhead Goal
Resource | % Overhead | Resource | % Overhead
Team Lead | 12% | Planning Manager | 12%
Chief Architect | 11% | Quality Assurance | 12%
Development Lead | 11% | Team | 11%

## Slide 19: Overhead Watchlist
Top 3 Overhead Activities (Non-Planning)
WP00.1.5 Standup Meeting
WP00.1.9: Planning & Tracking

## Slide 20: Overhead Watchlist - Planning

## Slide 21: Rework Costs

## Slide 22: Open Risks and Mitigation Strategies [5 min] - Team
ARGONAUTS

## Slide 23: Mentor Comments[12 min] - Team
ARGONAUTS